## AP
Accounts Payable
|  | Items to Test: |  |  | 112
[7 empty] | Dependencies: |  |  | 3 | Resolved: |  | 0
|  | Performs as Expected: |  |  | 0
Dependencies
|  | Total Items | Tested | Performs as Expected | Issue Found | ACS - Not Started | ACS - In Process | User Test | Hold | Post Upgrade | From Other Depts | < = Resolved | To Other Depts | < = Resolved | Comments
|  | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0
AP1 | MAINTAIN VENDORS | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AP1-1 | FIND AN EXISTING VENDOR
AP1-2 | ADD A NEW ADDRESS
AP1-3 | ADD A NEW LOCATION
AP1-4 | ADD A NEW 1099 CLASS
AP1-5 | ADD AN ALTERNATE NAME
AP1-6 | CHANGE REMIT TO VENDOR ON LOCATION
AP1-7 | ADD A NEW VENDOR
AP1-8 | DELETE A VENDOR
AP1-9 | INACTIVATE AN EXISTING VENDOR
AP1-10 | ADD ACH
AP1-11 | ADD CONTACT
AP1-12 | WHAT HAS BEEN CUSTOMIZED
AP1-13 | THE "DELETE" CHECK BOX
AP1-14 | VENDOR TIN
AP1-15 | EMPLID
AP1-16 | ENTERED, BY/MAINTAINED, BY/ LAST UPDATE
AP1-17 | FORM W-9 CHECK BOX/DATE W-9 RECEIVED
AP1-18 | APPROVAL DATE/BY
AP1-19 | NAME CHANGE PAGE,
AP1-20 | ACH PAYMENT METHOD UPDATES,
AP1-21 | VENDOR ADDR/PAYMENT ALTERNATE NAME DISPLAY
AP2 | CONTROL GROUPS | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AP2-1 | FIND AN EXISTING CONTROL GROUP
AP2-2 | ADD A CONTROL GROUP
AP2-3 | DELETE A CONTROL GROUP
AP2-4 | POST A CONTROL GROUP
AP3 | ENTERING VOUCHER INFORMATION | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0
AP3-1 | FIND AN EXISTING VOUCHER
AP3-2 | ADD A REGULAR VOUCHER
AP3-3 | ADD A PO VOUCHER | [9 empty] | PR2-3
AP3-4 | ADD A PO VOUCHER AGAINST A RECURRING PO WITH CORRESPONDING RELEASES | [9 empty] | PR3-2
AP3-5 | ADD A VOUCHER AGAINST A DISCOUNT VENDOR
AP3-6 | ADD A VOUCHER AGAINST A REPORTABLE VENDOR
AP3-7 | ENTER AN (CREDIT) ADJUSTMENT
AP3-8 | ENTER A JOURNAL VOUCHER
AP3-9 | ENTER A REVERSAL VOUCHER
AP3-10 | VERIFY VENDOR STATUS(1099, INACTIVE, ETC)
AP3-11 | VERIFY VOUCHER STATUS/CORRECT IF NEEDED
AP3-12 | SAVE VOUCHER
AP3-13 | VERIFY PAYEE/PAYMENT ADDRESS/CHANGE IF NEEDED
AP3-14 | PAYMENT ALTERNATE NAME DIPLAY
AP3-15 | VERIFY PAYMENT METHOD/CHANGE IF NEEDED
AP3-16 | RUN DOCUMENT TOLERANCE FOR PO VOUCHERS
AP3-17 | RUN VOUCHER BUDGET CHECK
AP3-18 | RUN VOUCHER POST | [11 empty] | GA1-18
AP3-19 | CHECK VOUCHER ACCOUNTING LINE
AP4 | MAINTAIN CONTRACTS | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AP4-1 | FIND AN EXISTING CONTRACT
AP4-2 | CREATE A NON PO CONTRACT
AP4-3 | CREATE A CONTRACT WITH NEGATIVE LINES (WITHHOLDING)
AP4-4 | STAGE RELEASES FOR NON PO CONTRACTS
AP4-5 | CREATE RECURRING RELEASES FOR PO CONTRACTS
AP4-6 | CREATE RECURRING RELEASES FOR CONTRACTS WITH NEGATIVE LINES (WITHHOLDING)
AP4-7 | REVIEW STAGED RELEASES
AP4-8 | DELETE STAGED RELEASES
AP4-9 | RUN VOUCHER BUILD (BUILD STAGED RELEASES)
AP4-10 | VERIFY DATA
AP4-11 | REVIEW AND CORRECT BATCH VOUCHER ERRORS AND PRE-EDIT ERRORS
AP4-12 | RUN DOCUMENT TOLERANCE IF BUILDING PO STAGED VOUCHERS
AP4-13 | RUN VOUCHER BUDGET CHECK
AP4-14 | RUN VOUCHER POST
AP4-15 | CHECK VOUCHER ACCOUNTING LINE
AP5 | PROCESSING PAYMENTS | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AP5-1 | CANCEL A PAYMENT(VOID/VOID AND REISSUE/VOID AND PUT ON HOLD)
AP5-2 | CANCEL A PAYMENT AGAINST A PURCHASE ORDER- VOID AND CLOSE (CHECK PO ENCUMBRANCE)
AP5-3 | INQUIRE ON A PAYMENT
AP5-4 | REVIEW A PAYMENT
AP5-5 | CREATE AN EXPRESS PAYMENT
AP5-6 | CREATE A PAYCYCLE
AP5-7 | CREATE AN ACH PAYCYCLE
AP5-8 | CREATE AN EFT PAYCYCLE
AP5-9 | ACT ON POTENTIAL LOST DISCOUNT
AP5-10 | ACT ON WITHHOLDING ALERT
AP5-11 | RESTART PAYCYCLE
AP5-12 | RESET PAYCYCLE
AP5-13 | PRINT TRIAL REGISTER
AP5-14 | PRINT CHECKS
AP5-15 | RUN PAYMENT POST
AP5-16 | CHECK VOUCHER ACCOUNTING LINE
AP6 | MANUAL PAYMENTS | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AP6-1 | RECORD A MANUAL CHECK
AP6-2 | POST A MANUAL PAYMENT
AP6-3 | VOID A MANUAL PAYMENT
AP6-4 | CORRECT A MANUAL PAYMENT
AP6-5 | POST CORRECTION
AP6-6 | CHECK VOUCHER ACCOUNTING LINE
AP7 | CAMPUS ORDERS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AP7-1 | ENTER A CAMPUS ORDER
AP7-2 | VERIFY CAMPUS ORDER SUMMARY
AP8 | EDI PROCESSING | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AP8-1 | RUN EDI FOR EVERY SATELLITE
AP8-2 | RUN VOUCHER BUILD
AP8-3 | VERIFY DATA
AP8-4 | REVIEW AND CORRECT BATCH VOUCHER ERRORS AND PRE-EDIT ERRORS
AP8-5 | RUN BUDGET CHECK
AP8-6 | RUN VOUCHER POST
AP8-7 | CHECK VOUCHER ACCOUNTING LINE
AP8-8 | USAP0015 (DUPLICATE INVOICE/SQR)
AP8-9 | USRECON (AP ACCOUNT POSITIVE PAY/SQR)
AP8-10 | USLP0001 (LPC POSITIVE PAY/SQR)
AP8-11 | UAP0005 (PAYMENT DISCOUNT POST/SQR)
AP8-12 | USAP0012 (VENDOR DELTE/SQR)
AP8-13 | USAPH008 (GRADUATE STIPENDS/SQR)
AP8-14 | SFAPLOAD (IA VENDOR LOAD/SQR)
AP8-15 | USAP0016 (AUDIT FILES/SQR)
AP9 | MCMP | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AP9-1 | PRINT CHECKS
AP9-1 | SPOIL CHECKS
AP9-1 | SPOIL FORMS
AP9-1 | UPDATE SECURITY
AP9-1 | UPDATE ENTITIES
AP10 | LP CHECKS-ORDERS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AP10-1 | ADD/UPDATE CUSTODIANS
AP10-2 | POSITIVE PAY WEB APP
AP11 | WITHHOLDING | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AP11-1 | UPDATE VOUCHER LINE WITHHOLDINGS
AP12 | EPIC PAYMENT | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AP12-1 | RECORD AN EPIC PAYMENT
AP12-2 | POST AN EPIC PAYMENT
AP12-3 | VOID AN EPIC PAYMENT
AP12-4 | CORRECT A EPIC PAYMENT
AP12-5 | POST EPIC CORRECTION
AP12-6 | CHECK VOUCHER ACCOUNTING LINE FOR EPIC PAYMENT

## FIS
Financial Solutions
|  | Items to Test: |  |  | 46
[7 empty] | Dependencies: |  |  | 0 | Resolved: |  | 0
|  | Performs as Expected: |  |  | 0
Dependencies
|  | Total Items | Tested | Performs as Expected | Issue Found | ACS - Not Started | ACS - In Process | User Test | Hold | Post Upgrade | From Other Depts | < = Resolved | To Other Depts | < = Resolved | Comments
|  | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FS1 | U of U WEP Apps | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FS1-1 | WEBFTP
FS1-2 | WEB Journal Upload
FS1-3 | Management Reports
FS1-4 | EBT
FS1-5 | Student Financial Drill down
FS1-6 | FIL/HRIL
FS1-7 | PCARD CF Validation (coordinate with Purchasing)
FS1-8 | Travel System Front‐end
FS2 | PeopleTools Components | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FS2-1 | GENKEY
FS2-2 | Enterprise Email
FS2-3 | Chartfield Validation
FS2-4 | Where‐Art‐Thou” Utility
FS2-5 | MCMP (coordinate with SOM testing)
FS2-6 | MCMP uploads for UMB
FS2-7 | E‐journal
FS2-8 | Chartfield query for Kronos
FS3 | Miscellaneous Batch processes | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FS3-1 | Name Sync
FS3-2 | Project CF Value Sync
FS3-3 | Report Ledger
FS3-4 | Incremental
FS3-5 | Rebuild
FS3-6 | BOBJ
FS3-7 | Ledger
FS3-8 | Chartfield dimensions
FS4 | Other Miscellaneous | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FS4-1 | FMAX integration
FS4-2 | Skire integration
FS4-3 | Travel CF validation
FS5 | Query | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FS5-1 | Test all FIL Queries
FS5-2 | Activity Repots
FS5-3 | Chartfields
FS5-4 | Claim on Cash
FS5-5 | EBT Reports
FS5-6 | Endowment Repts
FS5-7 | Grants/Contract
FS5-8 | Procure/Payment
FS5-9 | Security
FS5-10 | Test Endowment Report
FS5-11 | Run Ledger Diagnostic Queries (Report Ledger to Actuals)
FS5-12 | Report Ledger Actuals
FS5-13 | Report Ledger PTD Encumbrance
FS5-14 | Projects Budget
FS5-15 | Activities Budget
FS5-16 | Activities Encumbrance
FS5-17 | Org Validate
FS5-18 | Bu Validate
FS5-19 | Troubleshoot Query Issues

## GA
General Accounting
|  | Items to Test: |  |  | 42
[7 empty] | Dependencies: |  |  | 1 | Resolved: |  | 0
|  | Performs as Expected: |  |  | 0
Dependencies
|  | Total Items | Tested | Performs as Expected | Issue Found | ACS - Not Started | ACS - In Process | User Test | Hold | Post Upgrade | From Other Depts | < = Resolved | To Other Depts | < = Resolved | Comments
|  | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
GA1 | Journals | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
GA1-1 | Journal Entries
GA1-2 | Enter a new one
GA1-3 | Edit, Budget check, & Post
GA1-4 | Stress test on Budget Check
GA1-5 | Using the Button on the JE Page
GA1-6 | Using the Process Scheduler
GA1-7 | Copy a Journal
GA1-8 | Thermidor Journals including Reversals
GA1-9 | Interface File (Journals) Processing
GA1-10 | Merge Files
GA1-11 | Reformat Files
GA1-12 | External Journal Load
GA1-13 | Budget Journals
GA1-14 | Load a Journal
GA1-15 | Enter a Journal
GA1-16 | Edit and Budget Check
GA1-17 | Using the Button on the JE Page
GA1-18 | Using the Process Scheduler
GA1-19 | Journal Generation | [9 empty] | AP2-23
GA2 | Chartfields | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GA2-1 | Activity and Project Setup and Modification
GA2-2 | Create a new record and modify an existing record
GA2-3 | Combination Edit Administration
GA2-4 | Create a new record and modify an existing record
GA2-5 | Custom Account Description Maintenance
GA2-6 | Liaison Update
GA3 | Web Apps | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GA3-1 | Accounting Calendar Update
GA3-2 | Management Report Security Maintenance
GA3-3 | Download to Excel
GA3-4 | Create Monthly Management Reports
GA3-5 | e-Journal
GA3-6 | e-Journal Excel
GA4 | General | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GA4-1 | Allocations
GA4-2 | Close Ledgers
GA4-3 | FA/Payroll Disencumbrance
GA4-4 | Maintain Ledgers – Open and Close Accounting Periods
GA4-5 | Payroll Benefit Encumbrance Create
GA4-6 | Petty Cash Administration
GA4-7 | Queries
GA4-8 | Running
GA4-9 | State Audit File Creation
GA4-10 | Writing
GA4-11 | nVision Reporting

## GC
Grants and Contracts Accounting
|  | Items to Test: |  |  | 31
[7 empty] | Dependencies: |  |  | 0 | Resolved: |  | 0
|  | Performs as Expected: |  |  | 0
Dependencies
|  | Total Items | Tested | Performs as Expected | Issue Found | ACS - Not Started | ACS - In Process | User Test | Hold | Post Upgrade | From Other Depts | < = Resolved | To Other Depts | < = Resolved | Comments
|  | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GA1 | Set up Scholarship/Fellowships contracts, then notify Purchasing and Accounts Payable | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GA1-1 | Without withholding
GA1-2 | With withholding
GA2 | Create Projects | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GA2-1 | Create Projects with PeopleSoft project create screen
GA3 | Generate awards | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GA3-1 | One project, different PI and Account Executive
GA3-2 | Two projects
GA3-3 | One Projects Preliminary
GA3-4 | Regenerate Preliminary
GA4 | Budget Journals | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GA4-1 | Create Budget journals for newly created projects
GA4-2 | Edit Budget journals for newly created projects
GA4-3 | Post Budget journals for newly created projects
GA5 | Create F&A rate journal for newly created projects | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GA5-1 | Edit F&A rate journal
GA5-2 | Post F&A rate journal
GA5-3 | Combination Edit F&A rate journal
GA6 | Combination Edit | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GA6-1 | Create combination edit for newly created projects
GA7 | F&A Tree | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GA7-1 | Place projects on F&A tree
GA8 | Journal entry between newly created projects and established projects | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GA8-1 | Create journal entry between newly created projects and established projects
GA8-2 | Edit
GA8-3 | Post
GA9 | F&A | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GA9-1 | Run F&A processes
GA9-2 | Expense
GA9-3 | Encumbrances
GA9-4 | Check FA on newly created projects
GA10 | Attributes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GA10-1 | Modify attributes on established projects
GA11 | LOC | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GA11-1 | Run LOC Draw report
GA11-2 | Run LOC History report
GA12 | Queries | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GA12-1 | Run queries
GA13 | Look at web reports | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GA13-1 | Project Lookup
GA13-2 | Liaison Update
GA14 | ARRA | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GA14-1 | Files exist
GA14-2 | File export works
GA15 | 90 Day Letters | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GA15-1 | Gen Key run 90 day letters

## IA
Income Accounting
|  | Items to Test: |  |  | 4
[7 empty] | Dependencies: |  |  | 0 | Resolved: |  | 0
|  | Performs as Expected: |  |  | 0
Dependencies
|  | Total Items | Tested | Performs as Expected | Issue Found | ACS - Not Started | ACS - In Process | User Test | Hold | Post Upgrade | From Other Depts | < = Resolved | To Other Depts | < = Resolved | Comments
|  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IA1 | Income Accounting | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IA1-1 | All processes for Departmental Deposits.
IA1-2 | All processes for student refund checks and direct deposits.
IA1-3 | All processes for credit card application.
IA1-4 | All queries through Financials.

## MB
Managerial Banking & Operational Investments
|  | Items to Test: |  |  | 3
[7 empty] | Dependencies: |  |  | 0 | Resolved: |  | 0
|  | Performs as Expected: |  |  | 0
Dependencies
|  | Total Items | Tested | Performs as Expected | Issue Found | ACS - Not Started | ACS - In Process | User Test | Hold | Post Upgrade | From Other Depts | < = Resolved | To Other Depts | < = Resolved | Comments
|  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IA1 | Managerial Banking & Operational Investments | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IA1-1 | Test Cash Interest Distribution System (CID)
IA1-2 | Run SQR UCGLC003 – Cash Interest Distribution
IA1-3 | Run SQR UCGLC003 – Cash Interest Distribution Summary

## OSP
Office of Sponsored Projects
|  | Items to Test: |  |  | 27
[7 empty] | Dependencies: |  |  | 0 | Resolved: |  | 0
|  | Performs as Expected: |  |  | 0
Dependencies
|  | Total Items | Tested | Performs as Expected | Issue Found | ACS - Not Started | ACS - In Process | User Test | Hold | Post Upgrade | From Other Depts | < = Resolved | To Other Depts | < = Resolved | Comments
|  | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IA1 | PeopleSoft | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IA1-1 | Adding a new proposal.
IA1-2 | Copy a proposal.
IA1-3 | Update a proposal.
IA1-4 | Add budget header and budget line summary.
IA1-5 | Set up a Preliminary project.
IA1-6 | Add supplemental funding to a project.
IA1-7 | Submit proposal
IA1-8 | Generate Award
IA1-9 | Add new sponsor
IA1-10 | Build IRS Table Process
IA1-11 | Update Eligible PIs Process
IA1-12 | Bucksheet Process
IA1-13 | Queries
IA2 | VP/Board of Trustees Reports: | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IA2-1 | USGM0001
IA2-2 | USGM0002
IA2-3 | USGM0003
IA2-4 | USGM0004
IA2-5 | USGM0005
IA2-6 | USGM0006
IA2-7 | USGM0007
IA2-8 | USGM0008
IA2-9 | USGM0009
IA2-10 | USGM0010
IA2-11 | USGM0011
IA3 | Web Applications: | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IA3-1 | eProposal
IA3-2 | Research Portal
IA3-3 | Web Detail Reports

## PC
PCARD PORTAL (PRO)
|  | Items to Test: |  |  | 35
[7 empty] | Dependencies: |  |  | 0 | Resolved: |  | 0
|  | Performs as Expected: |  |  | 0
Dependencies
|  | Total Items | Tested | Performs as Expected | Issue Found | ACS - Not Started | ACS - In Process | User Test | Hold | Post Upgrade | From Other Depts | < = Resolved | To Other Depts | < = Resolved | Comments
|  | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PC1 | Employees | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PC1-1 | Add new
PC1-2 | Existing - Add training
PC1-3 | Create card
PC1-4 | Duplicate Card
PC1-5 | Issues - Add Inquiry
PC1-6 | Add - Violation
PC2 | Cards | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PC2-1 | Update information
PC2-2 | Change default chartfield
PC2-3 | Change limits
PC2-4 | Add/delete reallocator
PC2-5 | Add/delete chartfields
PC2-6 | Send chartfields to excel
PC2-7 | Add exemptions
PC2-8 | Add Permission
PC3 | Department | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PC3-1 | Add new department
PC3-2 | Existing Dept - Update information
PC3-3 | Audit History - add audit
PC3-4 | Add/view attachments
PC3-5 | Dept Notes - Add note/upload attachment
PC4 | Audits | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PC4-1 | Quick Audit Entry - Gen Info-add note
PC4-2 | Dept Audit Relationship - Add dept
PC5 | Maintenance | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PC5-1 | Pcard Code Maintenance
PC5-2 | -Inquiries
PC5-3 | -Violations
PC5-4 | -Cancellation
PC5-5 | -Exemptions
PC5-6 | Duplicate Card
PC5-7 | Cancel Card
PC5-8 | Un-Cancel Card
PC5-9 | Universal Reallocator
PC5-10 | Special Rights
PC5-11 | Audit Reports - Run
PC6 | Chartfield Validation - | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PC6-1 | Invalid - to excel
PC6-2 | Run validation
PC6-3 | Invalid Chartfield Search - Indv CH

## PL
Plant Operations
|  | Items to Test: |  |  | 6
[7 empty] | Dependencies: |  |  | 0 | Resolved: |  | 0
|  | Performs as Expected: |  |  | 0
Dependencies
|  | Total Items | Tested | Performs as Expected | Issue Found | ACS - Not Started | ACS - In Process | User Test | Hold | Post Upgrade | From Other Depts | < = Resolved | To Other Depts | < = Resolved | Comments
|  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PL1 | FMAX | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PL1-1 | Customer Work Request
IA1-2 | FMAX-Kronos integration
IA1-3 | AP Vouchers
IA1-4 | PCard Transactions
IA1-5 | Web Journal Processing
IA1-6 | Billing Integration

## PT
Property Accounting
|  | Items to Test: |  |  | 43
[7 empty] | Dependencies: |  |  | 0 | Resolved: |  | 0
|  | Performs as Expected: |  |  | 0
Dependencies
|  | Total Items | Tested | Performs as Expected | Issue Found | ACS - Not Started | ACS - In Process | User Test | Hold | Post Upgrade | From Other Depts | < = Resolved | To Other Depts | < = Resolved | Comments
|  | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PT1 | DEPRECIATION | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PT1-1 | DEPRECIATION CALCULATION AMDPCALC
PT1-2 | ACCOUNTING ENTRY CREATION AMAEDIST
PT1-3 | DEPRECIATION CLOSE AMDPCLOS
PT1-4 | LOAD DEPR REPORTING TABLE LOAD DEPR RPT
PT1-5 | LOAD NET BOOK VALUE TABLE AMLDNBVT
PT2 | ASSETS | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PT2-1 | ASSET LOCATION UPDATE USFA0021
PT2-2 | BLANK BOOKS USFA0019 CAUTION! This removes blank books from Cost!
PT2-3 | FEDERAL PERCENT UPDATE USFA0020
PT2-4 | UPDATE ACQUISITION PROJECT USFA001
PT2-5 | MASS CHANGE MASSCHNG
PT2-6 | TRANSACTION LOADER AMIF1000
PT2-7 | WEEKLY RETRIEVAL FROM GL USFA0008 SQR
PT2-8 | AM/GL COMPARE USFA0007 SQR
PT3 | REPORTS | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PT3-1 | BATCH RETRIEVAL USFA0002 SQR & CRYSTAL Fix Step order on Process Scheduler Request screen
PT3-2 | CAPITAL INVENTORY USFA0003 SQR
PT3-3 | CAPITAL EQUIPMENT LIST USFA0004 SQR & CRYSTAL
PT3-4 | DEPRECIATION REPORT USFA0005 SQR & CRYSTALS (2)
PT3-5 | GOVERNMENT EQUIPMENT USFA0013 SQR
PT3-6 | INSURABLE EQUIPMENT USFA0014 SQR
PT3-7 | UOFU ERROR REPORTS (ORG) USFA0016 SQR
PT3-8 | UOFU ERROR REPORTS (COST) USFA0017 SQR
PT3-9 | UOFU ERROR REPORTS (BOOK & COST) USFA0018 SQR
PT4 | APPLICATIONS | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PT4-1 | ADD ASSET
PT4-2 | DELETE ASSET
PT4-3 | ADD PARENT ASSET
PT4-4 | DELETE PARENT ASSET
PT4-5 | ADD CHILD ASSET
PT4-6 | DELETE CHILD ASSET
PT4-7 | RETIRE SALE
PT4-8 | RETIRE SCRAP
PT4-9 | RETIRE TRADE-IN
PT4-10 | REINSTATE
PT4-11 | ADJUST
PT4-12 | TRANSFER INTRA
PT4-13 | TRANSFER BU01 TO BU02
PT4-14 | ADD ASSET THRU UU ACQ PROJECT
PT4-15 | CHANGE LOCATION
PT4-16 | RECATEGORIZE
PT4-17 | CHANGE LIFE
PT4-18 | CHANGE PROFILE
PT4-19 | ADD NEW ORG IN CUSTODIAN
PT4-20 | ADD NEW MANUFACTURER
PT4-21 | ADD NEW RECORD IN GOVT REPORT INFO

## PR
Purchasing
|  | Items to Test: |  |  | 32
[7 empty] | Dependencies: |  |  | 2 | Resolved: |  | 0
|  | Performs as Expected: |  |  | 0
Dependencies
|  | Total Items | Tested | Performs as Expected | Issue Found | ACS - Not Started | ACS - In Process | User Test | Hold | Post Upgrade | From Other Depts | < = Resolved | To Other Depts | < = Resolved | Comments
|  | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
PR1 | Requisition | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR1-1 | Requisition entry
PR1-2 | Requisition budget check
PR1-3 | Requisition selection
PR1-4 | Requisition workbench
PR1-5 | Proof requisition add, create, print, re-print
PR2 | Purchase Orders | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
PR2-1 | PO reservation
PR2-2 | PO calculation
PR2-3 | PO creation | [11 empty] | AP3-3
PR2-4 | PO budget check
PR2-5 | PO document tolerance
PR2-6 | PO print
PR2-7 | PO dispatch
PR2-8 | PO lookup (web)
PR2-9 | PO voucher history (web)
PR2-10 | PO recon (PO close)
PR2-11 | PO re-open (new to version 9)
PR2-12 | PO change order (change order template)
PR2-13 | PO change order/modification on existing, vouchered POs
PR2-14 | PO monthly Crystal reports
PR2-15 | PO workbench
PR3 | Vouchers | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
PR3-1 | Voucher re-budget check
PR3-2 | Recurring voucher contract entry (PO contract stage) | [11 empty] | AP3-4
PR3-3 | Voucher lookup (web)
PR3-4 | Vendor
PR3-5 | Vendor add
PR3-6 | Vendor modification
PR3-7 | Vendor lookup (web)
PR4 | Other | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR4-1 | KK duplicate utility
PR4-2 | Ship-to code add and update
PR4-3 | Standard comment add and update
PR4-4 | Where art thou (WAT) report
PR4-5 | Query running, adding and updating

## SJ
Scheduled Jobs
|  | Items to Test: |  |  | 25
[7 empty] | Dependencies: |  |  | 0 | Resolved: |  | 0
|  | Performs as Expected: |  |  | 0
Dependencies
|  | Total Items | Tested | Performs as Expected | Issue Found | ACS - Not Started | ACS - In Process | User Test | Hold | Post Upgrade | From Other Depts | < = Resolved | To Other Depts | < = Resolved | Comments
|  | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SJ1 | APSCHED | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SJ1-1 | APDAILY – J - Accounts Payable
SJ1-2 | USLP0001 – SQR - Accounts Payable
SJ2 | CCSCHED | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SJ2-1 | USWCC004 – SQR
SJ2-2 | USWCC005 – SQR
SJ2-3 | USWCC006 – SQR
SJ2-4 | USWCC008 – SQR
SJ3 | GLSCHED | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SJ3-1 | UUU_ORGID_EX – AE
SJ3-2 | USGLH040 – SQR
SJ3-3 | UU_HSC_DW – AE
SJ3-4 | RPT_BOBR – J
SJ3-5 | USGLH023 – SQR
SJ3-6 | RPT_BOB – J
SJ3-7 | USPO0002 – SQR
SJ3-8 | MCMP – J
SJ3-9 | UU_PROJ_SYNC – AE
SJ4 | GMSCHED | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SJ4-1 | UU_GM_IRS – AE
SJ4-2 | UAGM0001 – AE
SJ4-3 | UU_GM_FED_SP – AE
SJ5 | PSSCHED | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SJ5-1 | PSXPARCHATTR – AE
SJ5-2 | PRCSSRVCLN – AE
SJ5-3 | PRCSYSPURGE – AE
SJ6 | SFSCHED | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SJ6-1 | UUSF1 – J
SJ7 | SKIRESCHED | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SJ7-1 | UU_PCARD – AE
SJ7-2 | UU_SK_INT_VC – AE
SJ7-3 | UU_SK_INT – AE
SJ8 | TRSSCHED | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SJ8-1 | TRVFEED – J

## SM
School of Medicine
|  | Items to Test: |  |  | 18
[7 empty] | Dependencies: |  |  | 0 | Resolved: |  | 0
|  | Performs as Expected: |  |  | 0
Dependencies
|  | Total Items | Tested | Performs as Expected | Issue Found | ACS - Not Started | ACS - In Process | User Test | Hold | Post Upgrade | From Other Depts | < = Resolved | To Other Depts | < = Resolved | Comments
|  | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SM1 | Crystal Reports: | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SM1-1 | Checks for Accuracy
SM1-2 | Comparison of Run Times to Prior Run Times
SM1-3 | Result Comparison to Prior Reports
SM2 | MCMP System | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SM2-1 | Summary Rev & Exp-Child Activ UCGLRC16 Crystal
SM2-2 | Summary Rev & Exp-Child Proj UCGLRC26 Crystal
SM2-3 | Budget Bal Avail (by OrgID) UCGLRD12 Crystal
SM2-4 | Sum Contract & Grants by OrgID UCGLRD13 Crystal
SM2-5 | Cash Bal Avail(by OrgID) UCGLRD14 Crystal
SM2-6 | Cash Balance Avail(by OrgID) UCGLRD15 Crystal
SM2-7 | Summary of Rev & Exp (Detail) UCGLRD16 Crystal
SM2-8 | Sum RevExp by Activity-Detail UCGLRD17 Crystal
SM2-9 | Sum of RevExp by Project-Detail UCGLRD27 Crystal
SM2-10 | Summary Rev & Exp-Parent Activ UCGLRP16 Crystal
SM2-11 | Summary Rev & Exp-Parent Proj UCGLRP26 Crystal
SM2-12 | Budget Bal Avail -Parent OrgID UCGLRS12 Crystal
SM2-13 | Sum Contracts & Grants-Parent UCGLRS13 Crystal
SM2-14 | Cash Bal Avail - Parent OrgID UCGLRS14 Crystal
SM2-15 | Cash Balance Avail-Rollup Org UCGLRS15 Crystal

## TX
Tax Accounting
|  | Items to Test: |  |  | 20
[7 empty] | Dependencies: |  |  | 0 | Resolved: |  | 0
|  | Performs as Expected: |  |  | 0
Dependencies
|  | Total Items | Tested | Performs as Expected | Issue Found | ACS - Not Started | ACS - In Process | User Test | Hold | Post Upgrade | From Other Depts | < = Resolved | To Other Depts | < = Resolved | Comments
|  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TX1 | Withholding Processes | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TX1-1 | Post Withholdings
TX1-2 | Withholding Voucher/Vendor Mismatch
TX1-3 | Withholding Adjustment
TX1-4 | Period Accumulation Adjustment
TX1-5 | Update Vendor Withholdings
TX1-6 | Update Voucher Line Withholdings
TX1-7 | Update Withholdings
TX1-8 | Withholding 1099 Report Post
TX1-9 | Withholding 1099 Report
TX1-10 | 1099 to Send Detail
TX1-11 | Print 1099 Copy B
TX1-12 | Withholding Sent File
TX1-13 | Create Reporting Information
TX1-14 | Withholding Report
TX1-15 | Withholding Control Report
TX1-16 | Withholding Report Information
TX1-17 | Vouchers by Vendor
TX1-18 | Vendor Balances by Class
TX1-19 | Period Accumulation Log
TX1-20 | Withholding Report by Class

## UH
University Hospital Accounting
|  | Items to Test: |  |  | 10
[7 empty] | Dependencies: |  |  | 0 | Resolved: |  | 0
|  | Performs as Expected: |  |  | 0
Dependencies
|  | Total Items | Tested | Performs as Expected | Issue Found | ACS - Not Started | ACS - In Process | User Test | Hold | Post Upgrade | From Other Depts | < = Resolved | To Other Depts | < = Resolved | Comments
|  | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UH1 | University Hospital Accounting | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UH1-1 | Reformat external journals
TX1-2 | External journal load
TX1-3 | Budget journal load
TX1-4 | Journal entry tasks - Add, Edit, Delete, Post
TX1-5 | Allocations
TX1-6 | Queries
TX1-7 | nVision Reports
TX1-8 | Org Id tasks - Add, Change, Inactivate
TX1-9 | Account tasks - Add, Change, Inactivate
TX1-10 | Trees - Add, Change, Delete

## Total
UPGRADE TOTALS
| Items to Test: |  |  | 447
[6 empty] | Dependencies: |  |  | 6 | Resolved: |  | 0
| Performs as Expected: |  |  | 0
Dependencies
| Total Items | Tested | Performs as Expected | Issue Found | ACS - Not Started | ACS - In Process | User Test | Hold | Post Upgrade | From Other Depts | < = Resolved | To Other Depts | < = Resolved | Comments
| 447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0
Accounts Payable | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0
Financial Solutions | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
General Accounting | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
Grants and Contracts Accounting | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Income Accounting | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Managerial Banking & Operational Investments | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Office of Sponsored Projects | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PCard Portal (PRO) | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Plant Operations | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Property Accouting | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Purchasing | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
Scheduled Jobs | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
School of Medicine | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tax Accounting | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
University Hospital Accounting | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0