## AP
Financial Services
|  | Items to Test: |  | 112 |  | Issue Found |  | 0 |  | User Test |  | 0
|  | Items Tested: |  | 103 |  | UIT - Not Started |  | 0 |  | Resolved by UIT |  | 1
|  | Performs as Expected |  | 103 |  | UIT - In Process |  | 0
Accounts Payable |  | Total Items | Tested | Performs as Expected | Issue Found | UIT - Not Started | UIT - In Process | User Test | Resolved by UIT | Hold | Post Upgrade | JIRA # | Comments
Items to Test |  | 112 | 103 | 103 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
AP1 | CONTROL GROUPS | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AP1-1 | FIND AN EXISTING CONTROL GROUP |  | 2024-04-19 | 2024-04-19
AP1-2 | ADD A CONTROL GROUP |  | 2024-04-19 | 2024-04-19
AP1-3 | DELETE A CONTROL GROUP |  | 2024-04-19 | 2024-04-19
AP1-4 | POST A CONTROL GROUP |  | 2024-04-19 | 2024-04-19
AP2 | ENTERING VOUCHER INFORMATION | 20 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AP2-1 | FIND AN EXISTING VOUCHER |  | 2024-04-19 | 2024-04-19
AP2-2 | ADD A REGULAR VOUCHER |  | 2024-04-19 | 2024-04-19
AP2-3 | ADD A PO VOUCHER |  | 2024-04-22 | 2024-04-22
AP2-4 | ADD A PO VOUCHER AGAINST A RECURRING PO WITH CORRESPONDING RELEASES |  | 2024-05-02 | 2024-05-02
AP2-5 | ADD A VOUCHER AGAINST A DISCOUNT VENDOR |  | 2024-04-22 | 2024-04-22
AP2-6 | ADD A VOUCHER AGAINST A REPORTABLE VENDOR |  | 2024-04-19 | 2024-04-19
AP2-7 | ENTER AN (CREDIT) ADJUSTMENT |  | 2024-04-22 | 2024-04-22
AP2-8 | ENTER A JOURNAL VOUCHER |  | 2024-04-22 | 2024-04-22
AP2-9 | ENTER A REVERSAL VOUCHER |  | 2024-04-22 | 2024-04-22
AP2-10 | VERIFY VENDOR STATUS(1099, INACTIVE, ETC) |  | 2024-04-22 | 2024-04-22
AP2-11 | VERIFY VOUCHER STATUS/CORRECT IF NEEDED |  | 2024-04-22 | 2024-04-22
AP2-12 | SAVE VOUCHER |  | 2024-04-19 | 2024-04-19
AP2-13 | VERIFY PAYEE/PAYMENT ADDRESS/CHANGE IF NEEDED |  | 2024-04-19 | 2024-04-19
AP2-14 | PAYMENT ALTERNATE NAME DIPLAY
AP2-15 | VERIFY PAYMENT METHOD/CHANGE IF NEEDED |  | 2024-05-02 | 2024-05-02
AP2-16 | RUN DOCUMENT TOLERANCE FOR PO VOUCHERS |  | 2024-05-02 | 2024-05-02
AP2-17 | RUN VOUCHER BUDGET CHECK |  | 2024-05-02 | 2024-05-02
AP2-18 | RUN VOUCHER POST |  | 2024-05-02 | 2024-05-02
AP2-19 | CHECK VOUCHER ACCOUNTING LINE |  | 2024-05-02 | 2024-05-02
AP2-20 | VOUCHER DISPLAY
AP3 | MAINTAIN CONTRACTS - RELEASES | 11 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AP3-1 | FIND AN EXISTING CONTRACT |  | 2024-04-22 | 2024-04-22
AP3-2 | STAGE RELEASES FOR NON PO CONTRACTS |  | 2024-05-01 | 2024-05-01
AP3-3 | STAGE RELEASES FOR PO CONTRACTS |  | 2024-04-22 | 2024-04-22
AP3-4 | REVIEW STAGED RELEASES |  | 2024-05-01 | 2024-05-01
AP3-5 | DELETE STAGED RELEASES |  | 2024-05-01 | 2024-05-01
AP3-6 | RUN VOUCHER BUILD (BUILD STAGED RELEASES)
AP3-7 | VERIFY DATA |  | 2024-05-01 | 2024-05-01
AP3-8 | REVIEW AND CORRECT BATCH VOUCHER ERRORS AND PRE-EDIT ERRORS
AP3-9 | RUN VOUCHER BUDGET CHECK
AP3-10 | RUN VOUCHER POST
AP3-11 | CHECK VOUCHER ACCOUNTING LINE
AP4 | PROCESSING PAYMENTS | 15 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AP4-1 | CANCEL A PAYMENT(VOID/VOID AND REISSUE/VOID AND PUT ON HOLD) |  | 2024-04-23 | 2024-04-23
AP4-2 | CANCEL A PAYMENT AGAINST A PURCHASE ORDER- VOID AND CLOSE (CHECK PO ENCUMBRANCE)
AP4-3 | INQUIRE ON A PAYMENT |  | 2024-04-23 | 2024-04-23
AP4-4 | REVIEW A PAYMENT |  | 2024-04-23 | 2024-04-23
AP4-5 | CREATE AN EXPRESS PAYMENT |  | 2024-04-23 | 2024-04-23
AP4-6 | CREATE A PAYCYCLE |  | 2024-04-23 | 2024-04-23
AP4-7 | CREATE AN ACH PAYCYCLE |  | 2024-04-23 | 2024-04-23
AP4-8 | ACT ON WITHHOLDING ALERT |  | 2024-04-23 | 2024-04-23
AP4-9 | RESTART PAYCYCLE |  | 2024-04-23 | 2024-04-23
AP4-10 | RESET PAYCYCLE |  | 2024-04-23 | 2024-04-23
AP4-11 | PRINT TRIAL REGISTER |  | 2024-04-23 | 2024-04-23
AP4-12 | PRINT CHECKS |  | 2024-04-23 | 2024-04-23
AP4-13 | RUN PAYMENT POST |  | 2024-05-02 | 2024-05-02
AP4-14 | CHECK VOUCHER ACCOUNTING LINE |  | 2024-05-02 | 2024-05-02
AP4-15 | PAY CYCLE - EFT |  | 2024-04-23 | 2024-04-23
AP5 | MANUAL PAYMENTS | 6 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AP5-1 | RECORD A MANUAL CHECK |  | 2024-04-22 | 2024-04-22
AP5-2 | POST A MANUAL PAYMENT |  | 2024-04-23 | 2024-04-23
AP5-3 | VOID A MANUAL PAYMENT |  | 2024-04-23 | 2024-04-23
AP5-4 | CORRECT A MANUAL PAYMENT |  | 2024-04-23 | 2024-04-23
AP5-5 | POST CORRECTION |  | 2024-04-23 | 2024-04-23
AP5-6 | CHECK VOUCHER ACCOUNTING LINE
AP6 | EDI PROCESSING | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
AP6-1 | RUN EDI FOR EVERY SATELLITE |  | 2024-04-23 | 2024-04-23
AP6-2 | RUN VOUCHER BUILD |  | 2024-04-23 | 2024-04-23
AP6-3 | VERIFY DATA |  | 2024-04-23 | 2024-04-23
AP6-4 | REVIEW AND CORRECT BATCH VOUCHER ERRORS AND PRE-EDIT ERRORS |  | 2024-04-18 | 2024-04-23 |  |  |  |  | Yes |  |  | FIN-9030
AP6-5 | RUN BUDGET CHECK |  | 2024-04-23 | 2024-04-23
AP6-6 | RUN VOUCHER POST |  | 2024-04-23 | 2024-04-23
AP6-7 | CHECK VOUCHER ACCOUNTING LINE |  | 2024-04-23 | 2024-04-23
AP6-8 | USAP0015 (DUPLICATE INVOICE/SQR) |  | 2024-04-23 | 2024-04-23
AP6-9 | USRECON (AP ACCOUNT POSITIVE PAY/SQR) |  | 2024-05-02 | 2024-05-02
AP6-10 | USLP0001 (LPC POSITIVE PAY/SQR) |  | 2024-05-02 | 2024-05-02
AP6-11 | UAP0005 (PAYMENT DISCOUNT POST/SQR) |  | 2024-05-02 | 2024-05-02
AP6-12 | USAP0017 – Vendor Load |  | 2024-04-23 | 2024-04-23
AP7 | MCMP | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AP7-1 | PRINT CHECKS |  | 2024-04-23 | 2024-04-23
AP7-2 | SPOIL CHECKS |  | 2024-04-23 | 2024-04-23
AP7-3 | UPDATE SECURITY |  | 2024-04-23 | 2024-04-23
AP7-4 | UPDATE ENTITIES |  | 2024-04-23 | 2024-04-23
AP8 | WITHHOLDING | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AP8-1 | UPDATE VOUCHER LINE WITHHOLDINGS |  | 2024-05-02 | 2024-05-02
AP9 | Security | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AP9-1 | Roll Verification |  | 2024-04-19 | 2024-04-19
AP9-2 | User Preference Setups |  | 2024-04-19 | 2024-04-19
AP10 | UShop Integration | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AP10-1 | SEND INVOICES FROM USHOP TO PEOPLESOFT |  | 2024-04-22 | 2024-04-22
AP10-2 | INVOICE STATUS UPDATE IS SENT BACK TO USHOP |  | 2024-04-22 | 2024-04-22
AP10-3 | Partial Penney |  | 2024-04-23 | 2024-04-23
AP11 | ePR | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AP11-1 | Create EPR voucher; for all types. |  | 2024-04-23 | 2024-04-23
AP11-2 | Check AP Section |  | 2024-04-23 | 2024-04-23
AP11-3 | Check round trip back. The voucher #, check # is listed back in EPR. |  | 2024-04-23 | 2024-04-23
AP11-4 | USAP0029- EPR Update |  | 2024-04-23 | 2024-04-23
AP11-5 | USAP0030- EPR Voucher Load/ File integration |  | 2024-04-23 | 2024-04-23
AP11-6 | USAP0031 - Address 500 (Will the BASS team be cover this one? If not, I have it listed with me.) |  | 2024-04-23 | 2024-04-23
AP11-7 | Run EDI |  | 2024-04-23 | 2024-04-23
AP11-8 | Run Voucher Build |  | 2024-04-23 | 2024-04-23
AP11-9 | Run Budget Check |  | 2024-04-23 | 2024-04-23
AP11-10 | Run Voucher Post |  | 2024-04-23 | 2024-04-23
AP12 | ePR-Web Section Review | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AP12-1 | JMPC Vendor (Communication Supply Corp Vn #9005) |  | 2024-04-23 | 2024-04-23
AP12-2 | Switch JMPC Vendor (Communication Supply Corp Vn #9005) to Check, review the AP Section |  | 2024-04-23 | 2024-04-23
AP12-3 | Multiple Remit address (Vertiv Vendor #67) |  | 2024-04-23 | 2024-04-23
AP12-4 | Multiple Location to Remit address (State of Utah Vn #833 Loc 15 -5, Loc 1-34) |  | 2024-04-23 | 2024-04-23
AP12-5 | Different 1099 Codes (Cicero Research Vn 200080) |  | 2024-04-23 | 2024-04-23
AP12-6 | NRA - Yes |  | 2024-04-23 | 2024-04-23
AP12-7 | NRA-No |  | 2024-04-23 | 2024-04-23
AP12-8 | NRA - Yes - New Vendor |  | 2024-04-23 | 2024-04-23
AP12-9 | NRA - Yes- Correction Vendor |  | 2024-04-23 | 2024-04-23
AP12-10 | NRA-Yes - AP Change |  | 2024-04-23 | 2024-04-23
AP12-11 | Different Location-ACH (MetPay 7308 Loc 1-3, Loc 2-2) |  | 2024-04-23 | 2024-04-23
AP12-12 | Accounting date |  | 2024-04-23 | 2024-04-23
AP12-13 | Amount- one line |  | 2024-04-23 | 2024-04-23
AP12-14 | Amount-Multiple lines with diff GL Codes |  | 2024-04-23 | 2024-04-23
AP12-15 | Amount- Expedite with one line |  | 2024-04-23 | 2024-04-23
AP12-16 | Amount -Expedite with multiple lines |  | 2024-04-23 | 2024-04-23
AP12-17 | Amount- Different Distributions with Negative amounts |  | 2024-04-23 | 2024-04-23
AP12-18 | Employee Verification Section (John Levandowski vn 18541-Non Active) |  | 2024-04-23 | 2024-04-23
AP12-19 | Terms |  | 2024-04-23 | 2024-04-23
AP12-20 | Handling Codes & Separate Payments Box |  | 2024-04-23 | 2024-04-23
AP12-21 | Payment Messages |  | 2024-04-23 | 2024-04-23
AP12-22 | AP Exception Flag |  | 2024-04-23 | 2024-04-23
AP12-23 | Approval bus stops are moving |  | 2024-04-23 | 2024-04-23
AP12-24 | Adding Approvers |  | 2024-04-23 | 2024-04-23

## BUR
Financial Services
|  | Items to Test: |  | 15 |  | Issue Found |  | 0 |  | User Test |  | 0
|  | Items Tested: |  | 0 |  | UIT - Not Started |  | 0 |  | Resolved by UIT |  | 0
|  | Performs as Expected |  | 0 |  | UIT - In Process |  | 0
Bursars Office |  | Total Items | Tested | Performs as Expected | Issue Found | UIT - Not Started | UIT - In Process | User Test | Resolved by UIT | Hold | Post Upgrade | JIRA # | Comments
Items to Test |  | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IA1 | Departmental Deposits | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IA1-1 | Use/Add a new value or find an existing value
IA1-2 | Use/Recap
IA1-3 | Setup/Dept Banks
IA1-4 | Setup/Deposit Types
IA1-5 | Process/Journal Load
IA2 | Security | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IA2-1 | Setup/IA Approvers
IA2-2 | Setup/Org ID Security
IA2-3 | Setup/Person Security
IA4 | Other Miscellaneous | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IA3-1 | All Processes for credit card application
IA3-2 | All queries through Financials.
IA3-3 | Student Refund Vendor Load (SFSCHED)
IA3-4 | Management Reports\Student Financial Drill down
IA3-5 | The "View" that validates the chart fields for Item Types in Student Financials, and the Speed Keys and Department receipt chart fields in Student Financial Cashiering
IA5 | Utilities | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IA4-1 | USE – Chart field Template – Use /Add a new value or find an existing value
IA6 | Credit Card | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IA5-1 | Setup/Security
IA5-2 | Setup/CC Security Apps
IA5-3 | Setup/Merchants
IA5-4 | Setup/Payment Types
IA5-5 | Setup/Secure Acceptance Security

## FRA
Financial Services
|  | Items to Test: |  | 45 |  | Issue Found |  | 1 |  | User Test |  | 0
|  | Items Tested: |  | 45 |  | UIT - Not Started |  | 0 |  | Resolved by UIT |  | 0
|  | Performs as Expected |  | 44 |  | UIT - In Process |  | 1
Financial Reporting and Accounting |  | Total Items | Tested | Performs as Expected | Issue Found | UIT - Not Started | UIT - In Process | User Test | Resolved by UIT | Hold | Post Upgrade | JIRA # | Comments
Items to Test |  | 45 | 45 | 44 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0
GA1 | Journals | 21 | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GA1-1 | Enter a new Journal |  | 2024-04-18 | 2024-04-18
GA1-2 | Edit, Budget check, & Post with button |  | 2024-04-18 | 2024-04-18
GA1-3 | Edit, Budget check, & Post Using the Process Scheduler |  | 2024-04-24 | 2024-04-24
GA1-4 | Copy a Journal |  | 2024-04-18 | 2024-04-18
GA1-5 | Delete a Journal |  | 2024-04-18 | 2024-04-18
GA1-6 | Thermidor Journals including Reversals |  | 2024-04-18 | 2024-04-18
GA1-7 | Merge Files |  | 2024-04-24 | 2024-04-24
GA1-8 | Reformat Files |  | 2024-04-24 | 2024-04-24
GA1-9 | External Journal Load |  | 2024-04-24 | 2024-04-24
GA1-10 | Enter Encumbrance Journal |  | 2024-04-18 | 2024-04-18
GA1-11 | Edit, Budget check, Encumbrance Journal with button |  | 2024-04-18 | 2024-04-18
GA1-12 | Load Encumbrance Journal |  | 2024-04-25 | 2024-04-25
GA1-13 | Edit, Budget check, Encumbrance Journal Using the Process Scheduler |  | 2024-04-24 | 2024-04-24
GA1-14 | Enter a Budget Journal |  | 2024-04-24 | 2024-04-24
GA1-15 | Load a Budget Journal |  | 2024-04-24 | 2024-04-24
GA1-16 | Post Budget Journal Using Button |  | 2024-04-24 | 2024-04-24
GA1-17 | Post Budget Journal Using the Process Scheduler |  | N/A | N/A
GA1-18 | Journal Generation |  | 2024-04-29 | 2024-04-29
GA1-19 | Test the integration of an e-journal into PeopleSoft |  | 2024-04-29 | 2024-04-29
GA1-20 | eJournal Integration |  | 2024-04-29 | 2024-04-29
GA1-21 | WEB Journal Processing |  | 2024-04-29 | 2024-04-29
GA2 | Chartfields | 6 | 6 | 5 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0
GA2-1 | Create a new ORG |  | 2024-04-29 |  | 2024-04-29 |  | 2024-05-01 |  |  |  | FIN-9067
GA2-2 | Create a new Activity and Project and modify an existing record |  | 2024-04-18 | 2024-04-18
GA2-3 | Create a new combo edit and modify an existing record |  | 2024-04-18 | 2024-04-18
GA2-4 | Custom Account Description Maintenance |  | 2024-04-18 | 2024-04-18
GA2-5 | Liaison Update |  | 2024-04-18 | 2024-04-18
GA2-6 | Chartfield Validation |  | 2024-04-29 | 2024-04-29
GA3 | Web Apps | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GA3-1 | Accounting Calendar Update |  | 2024-04-29 | 2024-04-29
GA3-2 | Management Reports |  | 2024-04-29 | 2024-04-29
GA3-3 | Management Report Security Maintenance |  | 2024-04-18 | 2024-04-18
GA3-4 | Download to Excel |  | 2024-04-29 | 2024-04-29
GA3-5 | e-Journal - Create, validate, submit and upload |  | 2024-04-29 | 2024-04-29
GA3-6 | Evidence of Review (EOR) |  | 2024-04-29 | 2024-04-29
GA3-7 | Management Reports |  | 2024-04-29 | 2024-04-29
GA3-8 | eJournal Upload from Excel |  | 2024-04-29 | 2024-04-29
GA4 | General | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GA4-1 | Allocations |  | 2024-04-29 | 2024-04-29
GA4-2 | Close Ledgers |  | 2024-04-29 | 2024-04-29
GA4-3 | Maintain Ledgers – Open and Close Accounting Periods - Open Period Update |  | 2024-04-29 | 2024-04-29
GA4-4 | Petty Cash Administration |  | 2024-04-18 | 2024-04-18
GA4-5 | Queries |  | 2024-04-29 | 2024-04-29
GA4-6 | Responsible Person Name Sync |  | 2024-04-29 | 2024-04-29
GA4-7 | Setup Management Report Access based on the Security Authorization Form |  | 2024-04-18 | 2024-04-18
GA4-8 | 10500 Cash Allocations |  | 2024-04-29 | 2024-04-29
GA4-9 | AFS SEC CLEANUP |  | N/A | N/A
GA4-10 | Generate AP Journals |  | 2024-04-29 | 2024-04-29
Items not to test but be aware of
GA5 | Journals
GA5-1 | Set Up Journal Source
GA6 | Chartfields
GA6-1 | Account Setup
GA6-2 | Fund Setup and Modification
GA7 | Web Apps
GA7-1 | Create Monthly Management Reports
GA7-2 | GFA
GA7-3 | Management Reports\EBT
GA8 | General
GA8-1 | FA/Payroll Disencumbrance
GA8-2 | Payroll Benefit Encumbrance Create
GA8-3 | Report Ledger - Partial
GA8-4 | Report Ledger - Full
GA8-5 | State Audit File Creation
GA8-6 | nVision Reporting
GA8-7 | Tree Viewer

## FSTS
Financial Services
|  | Items to Test: |  | 18 |  | Issue Found |  | 0 |  | User Test |  | 0
|  | Items Tested: |  | 18 |  | UIT - Not Started |  | 0 |  | Resolved by UIT |  | 1
|  | Performs as Expected |  | 18 |  | UIT - In Process |  | 0
Financial Services Technical Support |  | Total Items | Tested | Performs as Expected | Issue Found | UIT - Not Started | UIT - In Process | User Test | Resolved by UIT | Hold | Post Upgrade | JIRA # | Comments
Items to Test |  | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1
FS1 | U of U WEP Apps | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1
FS1-1 | WEB Journal Processing |  | 2024-04-18 | 2024-04-18
FS1-2 | Fund Lookup |  | 2024-01-18 | 2024-01-18
FS1-3 | Project Lookup |  | 2024-01-18 | 2024-01-18
FS1-4 | Activity Lookup |  | 2024-04-18 | 2024-01-18 |  |  |  |  | Yes |  | YES | FIN-9028 | Type ahead on Liaison update is not working properly. Val confirmed same issue exists in PROD, so this is not an upgrade issue and will be worked on post-upgrade
FS1-5 | FIL/HRIL |  | 2024-04-18 | 2024-01-18
FS1-6 | OrgID Lookup |  | 2024-01-18 | 2024-01-18
FS1-7 | GFA |  | 2024-01-18 | 2024-01-18
FS1-8 | General Stores |  | 2024-01-18 | 2024-01-18
FS1-9 | EOR |  | 2024-01-18 | 2024-01-18
FS1-10 | Asset Management |  | 2024-01-18 | 2024-01-18
FS1-11 | Reporting Org Lookup |  | 2024-01-18 | 2024-01-18
FS1-12 | Endowment Market Report |  | 2024-01-18 | 2024-01-18
FS1-13 | Chartfield Template |  | 2024-01-18 | 2024-01-18
FS1-14 | Ship to Lookup |  | 2024-01-18 | 2024-01-18
FS1-15 | Journal Detail Search |  | 2024-01-18 | 2024-01-18
FS1-16 | EBT Security |  | 2024-01-18 | 2024-01-18
FS2 | PeopleTools Components | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FS2-1 | GENKEY |  | 2024-01-18 | 2024-01-18
FS2-2 | Query Manager |  | 2024-01-18 | 2024-01-18
FS3 | GT Forms

## GC
Financial Services
|  | Items to Test: |  | 100 |  | Issue Found |  | 4 |  | User Test |  | 0
|  | Items Tested: |  | 73 |  | UIT - Not Started |  | 1 |  | Resolved by UIT |  | 0
|  | Performs as Expected |  | 69 |  | UIT - In Process |  | 3
Grants and Contracts Accounting |  | Total Items | Tested | Performs as Expected | Issue Found | UIT - Not Started | UIT - In Process | User Test | Resolved by UIT | Hold | Post Upgrade | JIRA # | Comments
Items to Test |  | 100 | 73 | 69 | 4 | 1 | 3 | 0 | 0 | 0 | 0 | 3
GC1 | PROJECT/AWARD/CONTACT SETUP (complete combo edit for all new projects) (OSP to GCA) | 8 | 7 | 6 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1
GC1-1 | Test with GC10-8 Project Number Validation Proposal A. Generate an F1 proposal preliminary project. Verify notification emails. Set up the Project, verify project department effective date equals project start date Set up combo edit. Verify no award/contract was created. Verify no budget posted. |  | 2024-04-24 | 2024-04-24
GC1-2 | Clear Prelim from GC1-1 Fully generating a preliminary (pre-sales spending) project/setting up the Project/Award/Contract (CR_NON_LOC Contract). Verify notification emails. Verify budget posting. (Proposal A) |  | 2024-04-26 | 2024-04-26
GC1-3 | Fully generating a cost reimbursable award/project/contract - GCA refuse notification (verify emails) - OSP renotify (verify emails) Set up the /Project/Award/Contract single project (CR_NON_LOC Contract). Combo Edit, Post Budget. Verify notification emails. (Propsal D)
GC1-4 | COMBO contract - Fully generating an F1 Proposal and setting up the /Project/Award/Contract, with a cost reimbursable and a fixed price project. Combo Edit, Post Budget. Verify notification emails. Verify separate contract lines created for cr and fp (Proposal N) |  | 2024-04-26 |  | 2024-04-26 |  | 2024-05-01 |  |  |  |  | FIN-9066
GC1-5 | CR_LOC AWARD, sponsor NIH. Fully generating an F1 Proposal with multiple cost reimbursable projects and a PRJE(s). Setting up the /Project/Award/Contract. Verify notification emails. Verify Project Role. (Proposal J) |  | 2024-04-24 | 2024-04-24
GC1-6 | Budget entry - Verify budget can't post on projects in Closed or Final status |  | 2024-04-26 | 2024-04-26
GC1-7 | Verify Workcenter |  | 2024-04-22 | 2024-04-22
GC1-8 | GEN FIXED PRICE - Fully generating an F1 Proposal and setting up the /Project/Award/Contract, with a fixed price project (FIXED_PRICE Contract) Verify notification emails. |  | 2024-04-26 | 2024-04-26
GC2 | BILLING - Contract types and Forms | 20 | 17 | 15 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 2
GC2-1 | Test with GC9-11, GC10--3 Run CR_LOC Draw - 907P, verify AP liabilities do not bill (MOD_BI_001) - coordinate with AP to make vendor discount vouchers and paid and unpaid vouchers
GC2-2 | Run LOC Draw History Report - quarterly reporting |  | 2024-04-22 | 2024-04-22 | [8 empty] | Fin-8131
GC2-3 | Test with GC10-15 Run CR_NON_LOC billing with GM_2COL Form with one contract line. Add billing header note verify it prints on the invoice. Test future/past dated invoices beyond 180 days (should be an error message) (FIN-2214) |  | 2024-04-22 | 2024-04-22 | [8 empty] | Fin-8131
GC2-4 | Run CR_NON_LOC billing with GM_4COL Form (using award with 4 or more projects, verify budget/expenses are correct on invoice form) |  | 2024-04-22 | 2024-04-22 | [8 empty] | Fin-8159
GC2-5 | Test with GC2-6 BP HOLD and GC2-7 DEFER BIL ROWS Run CR_NON_LOC billing with DATA_FORM Form |  | 2024-04-24 | 2024-04-24
GC2-6 | Test with GC2-5 Place CR_NON_LOC bill plan on HOLD, verify no biling interface is created (Test with GC2-5) |  | 2024-04-24 | 2024-04-24
GC2-7 | Test with GC2-5 Run CR_NON_LOC, DATA_FORM invoice, defer BIL line as of current date then run another bill to pick up the deferred bill line and create a second invoice. |  | 2024-04-24 | 2024-04-24
GC2-8 | Test with GC2-9 Correct Interface errors Run CR_NON_LOC billing with GM_270 Form - BIL only 1 - 3 rows |  | 2024-04-24 | 2024-04-24
GC2-9 | Test with GC2-8 Run CR_NON_LOC billing with 1-3 BIL rows after deleting billing specialist and invoice form on bill plan. Verify an interface error was created. Correct interface error by updating billing specialist and invoice form. Create invoice. |  | 2024-04-24 | 2024-04-24
GC2-10 | Test with GC2-11 DELETE WORKSHEET Run CR_NON_LOC billing with GM_103X Form |  | 2024-04-26 | 2024-04-26
GC2-11 | Test with GC2-10 Delete CR_NON_LOC Billing Worksheet and bill again |  | 2024-04-26 | 2024-04-26
GC2-12 | Run FIXED_PRICE bill on GM_FIX form (verify formatting on event page looks correct) |  | 2024-04-26 |  | 2024-04-26 |  | 2024-05-01 |  |  |  |  | FIN-9065
GC2-13 | Run CR_PREPAID event bill on GM_FIX form (verify formatting on event page looks correct) |  | 2024-04-26 |  | 2024-04-26 |  | 2024-05-01 |  |  |  |  | FIN-9063
GC2-14 | Run CR_PREPAID utilization invoice, NO_PRINT form (w/GC9-9 DEF REV ) |  | 2024-05-02 | 2024-05-02
GC2-15 | Run COMBO billing event bill on GM_FIX form Run COMBO billing on as incurred bill on GM_4COL form
GC2-16 | Reprint invoice through: Billing > Generate Invoices > Non-Consolidated > Reprint Invoices |  | 2024-05-01 | 2024-05-01
GC2-17 | Reprint invoice through: Billings > Locate Bills > Bills Invoiced, click print icon |  | 2024-04-26 | 2024-04-26
GC2-18 | Credit/Rebill, offset credit bill with original bill |  | 2024-04-26 | 2024-04-26
GC2-19 | Process Batch Billing with multiple bill lines - what can the system process before it fails?
GC2-20 | Check formatting on peoplesoft pages (ie event page) |  | 2024-04-22 | 2024-04-22
GC3 | AR-CGA | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GC3-1 | Verify items created in AR following billing updates and Arupdate
GC3-2 | Run ARUPDATE
GC3-3 | CR_LOC_PAYMENT
GC3-4 | Deposit with Regular Deposit
GC3-5 | Deposit with Express Deposit
GC3-6 | Apply a partial payment with Express Deposit
GC3-7 | Apply an overpayment with Express Deposit
GC3-8 | Credit memos/Debit Memos
GC3-9 | Refunds - create credit event item to refund. Run credit cr non loc to offset
GC3-10 | Offsets - create credit event item to offset. Run credit cr non loc to offset
GC3-11 | Unpost a payment
GC3-12 | Unpost a maintenance worksheet
GC3-13 | DEPOSIT REPORT BY ENTRY DATE
GC3-14 | Put a Payment On Account
GC4 | AWARD MOD - OSP generate mod, verify email notifications and GCA process MOD | 9 | 4 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
GC4-1 | Test with GC4-9 PI Change - Test Award Mod Decline, Renotify and Complete - Verify Email notifications
GC4-2 | Sponsor Change
GC4-3 | Test with GC10-5 Verify Project Task Defaults as '1' - not Add a New Value on Project Activity page Test with GC10-6 Project Dept Effective Date and Test with GC10-7 F&A Ready warning Add new contract line and project to CR_NON_LOC contract, post budget, amend contract
GC4-4 | Award reduction on FIXED_PRICE contract. Reduce budget and negotiated amount. |  | 2024-04-26 | 2024-04-26
GC4-5 | Award reduction on CR_PREPAID contract. Reduce budget and existing prepaid event line.
GC4-6 | Using UU Date Changes page extend end dates on multiple project award (U of U Applications > GM Applications > Process > UU Date Changes) verify end dates update on all pages including appropriate project team members. (Award Profile, Project Activities, Project, Project Team, Funding Tab and Contract Line) - verify management report end date updated. See 54503335 has multiple PLIAs, verify correct PLIA end date updated. |  | 2024-04-29 | 2024-04-29
GC4-7 | Manually change start and end dates on single project award - must update 8 areas: Award Profile, Project Activities, Project, Project Team, Project Location, Funding Tab and Contract Line. Verify dates updated on all pages including appropriate project team members and management report. |  | 2024-04-26 | 2024-04-26
GC4-8 | Test with GC4-1 Award mod Notify/Decline/Renotify/Complete - Verify email notifications for each step
GC4-9 | Copy Project Utility (new in FY 2021) – Feature allows us to copy an existing project to add a new project to a contract. This is a much more efficient way to add a project. Edit in place to only allow a unique 8 digit project number starting with 5 to be entered. Some fields have to be updated manually but the majority will be done with the copy process instead of a person having to enter in every single piece of data. |  | 2024-05-02 |  | 2024-05-02 | 2024-05-02
GC5 | To be verified by BASS | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GC5-1 | Project Lookup web reports |  | 2024-04-24 | 2024-04-24
GC5-2 | Check Management reports |  | 2024-04-24 | 2024-04-24
GC6 | PROCESSES RUN BY GCASCHED - GCADLYTM - how will these be run? | 16 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GC6-1 | PC_AP_TO_PC - Cost collection - test that only the appropriate costs cost collect.
GC6-2 | PC_GL_TO_PC - Cost collection - test that only the appropriate costs cost collect. |  | 2024-04-24 | 2024-04-24
GC6-3 | GM_GMFACS - F&A test that appropriate expense accounts have F&A applied based on the F&A Base. |  | 2024-04-24 | 2024-04-24
GC6-4 | PSA_ACCTGGL (Rev Rec - CA_ACCTG_LN_PC table) |  | 2024-04-24 | 2024-04-24
GC6-5 | BIJOB05 - Billing - Loads invoices to AR - Billing updates have to be run in this order: BIJOB05, BIJOB06, BIPCC000 and PC_BI_TO_PC |  | 2024-04-22 | 2024-04-22
GC6-6 | BIJOB06 - Billing - Creates accounting entries |  | 2024-04-22 | 2024-04-22
GC6-7 | BIPCC000 - Billing – Finalizes and inserts invoice in billing history |  | 2024-04-22 | 2024-04-22
GC6-8 | PC_BI_TO_PC - Billing - updates PROJ_RESOURCE |  | 2024-04-22 | 2024-04-22
GC6-9 | Process Deferred Revenue - After Utilization billing, PSA_ACCTGGL runs to put the 20700 in CA_ACCTG_LN_PC, then FSJGEN_ GMDR creates the GMDR journal. (w/GC2-14 PPD UTL) |  | 2024-05-02 | 2024-05-02
GC6-10 | Reprice preliminary transactions after clear prelim. Creates BIL rows for as incurred billing. (Pricing) |  | 2024-04-26 | 2024-04-26
GC6-11 | Test with GC2-1 Integrate AP vouchers, verify vendor discount and Unpaid (20099) and paid vouchers on CR_LOC invoicing (coordinate with AP)
GC6-12 | Integrate GL Transactions |  | 2024-04-24 | 2024-04-24
GC6-13 | Journal Generate Billing |  | 2024-04-22 | 2024-04-22
GC6-14 | Journal generate Revenue Recognition |  | 2024-04-24 | 2024-04-24
GC6-15 | Journal generate F&A |  | 2024-04-24 | 2024-04-24
GC6-16 | GCA DAILY |  | 2024-04-24 | 2024-04-24
GC7 | SYSTEM MODIFICATIONS | 10 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GC7-1 | Test with GC2-1 MOD_BI_001 excludes draw of AP Liability (20099) on CR_LOC billing
GC7-2 | Assign custom account description verify on management report - U of U Applications > GL Applications > Chartfield > Custom Account Descr |  | 2024-04-26 | 2024-04-26
GC7-3 | Test with GC4-4 When adding a project only allow Project Task to equal '1'; No Add a New Value on Project Activity Page (FIN-??) |  | 2024-05-01 | 2024-05-01
GC7-4 | PROJ DEPT EFF DATE EQUAL TO PROJ START DATE When adding a project Project Dept Effecvtive Date equals Project Start Date |  | 2024-05-01 | 2024-05-01
GC7-5 | Test with GC4-4 Error message pop up when adding a project if F&A Status not made Ready |  | 2024-05-01 | 2024-05-01
GC7-6 | Test with GC1-1 Project number validation on generate award |  | 2024-04-24 | 2024-04-24
GC7-7 | Setup billing specialist |  | 2024-04-29 | 2024-04-29
GC7-8 | Cognizant accountant |  | 2024-05-02 | 2024-05-02
GC7-9 | Future dated invoice error (180 days either way) |  | 2024-04-22 | 2024-04-22
GC7-10 | UU_USFS3048
GC8 | QUERIES | 21 | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GC8-1 | Run prebill query prior to running cost reimbursable invoices - GCA_BIL_PREBILL_REPORT |  | 2024-04-22 | 2024-04-22
GC8-2 | Run Pending events query prior to running event bill - GCA_PENDING_EVTS_TO_BE_BILLED |  | 2024-04-26 | 2024-04-26
GC8-3 | Run GCA_BIL_AND_OLT_BY_CONTRACT to show all BIL OLT lines on a contract line. |  | 2024-04-22 | 2024-04-22
GC8-4 | Check PROJ_RESOURCE for updates based on budget entry |  | 2024-04-24 | 2024-04-24
GC8-5 | Run GCA_A133_FED_AND_NON_FED_3 |  | 2024-04-24 | 2024-04-24
GC8-6 | Run GCA_AMOUNTS_IN_16400_16401 |  | 2024-04-29 | 2024-04-29
GC8-7 | Run GCA_AR_AGING_REPORT |  | 2024-04-29 | 2024-04-29
GC8-8 | Run GCA_AR_AGING_REPORT_NO_FINALS |  | 2024-05-01 | 2024-05-01
GC8-9 | Run GCA_BALSHEET0_STATUS_NOTFINAL |  | 2024-04-29 | 2024-04-29
GC8-10 | Run GCA_BILLSPEC_W_ACT_PRJ_AMOUNT |  | 2024-05-01 | 2024-05-01
GC8-11 | Run GCA_BILL_SPEC_W_ACT_PROJ_NO_F |  | 2024-05-01 | 2024-05-01
GC8-12 | Run GCA_UNAPPLIED_DEPOSITS |  | 2024-04-29 | 2024-04-29
GC8-13 | GCA_SETUP_PENDING_GENERATE |  | 2024-04-29 | 2024-04-29
GC8-14 | GCA_SETUP_COMBO_EDIT_CHK |  | 2024-04-24 | 2024-04-24
GC8-15 | GCA_BIL_IN_WKST_AND_NO_REG_INV |  | 2024-04-29 | 2024-04-29
GC8-16 | Run GCA_EXP_REV_COMPARE_YYYY (Changes each fiscal year) |  | 2024-04-29 | 2024-04-29
GC8-17 | Query GCA_SETUP_ADD_PROJECT |  | 2024-05-01 | 2024-05-01
GC8-18 | Run GCA_LOC_ITEMS_ALL_W_BALANCE |  | 2024-05-01 | 2024-05-01
GC8-19 | Change to: Run GCA_COSTSHARE_FUNDING_COMPARE |  | 2024-04-29 | 2024-04-29
GC8-20 | SET UP LOC QUERY |  | 2024-04-24 | 2024-04-24
GC8-21 | GCA_SETUP_CHECK_DATES (Test with GC4-7 UU Date Change Page) |  | 2024-04-29 | 2024-04-29

## OSP
VP for Research
|  | Items to Test: |  | 18 |  | Issue Found |  | 1 |  | User Test |  | 0
|  | Items Tested: |  | 17 |  | UIT - Not Started |  | 1 |  | Resolved by UIT |  | 0
|  | Performs as Expected |  | 16 |  | UIT - In Process |  | 0
Office of Sponsored Projects |  | Total Items | Tested | Performs as Expected | Issue Found | UIT - Not Started | UIT - In Process | User Test | Resolved by UIT | Hold | Post Upgrade | JIRA # | Comments
Items to Test |  | 18 | 17 | 16 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
OSP1 | PeopleSoft | 9 | 8 | 7 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
OSP1-1 | Adding a new proposal. |  | 2024-05-02 | 2024-05-02
OSP1-2 | Copy a proposal. |  | 2024-05-02 | 2024-05-02
OSP1-3 | Update a proposal. |  | 2024-04-24 | 2024-04-24
OSP1-4 | Add budget header and budget line summary. |  | 2024-04-24 | 2024-04-24
OSP1-5 | Set up a Preliminary project. |  | 2024-04-24 | 2024-04-24
OSP1-6 | Submit proposal |  | 2024-04-24 | 2024-04-24
OSP1-7 | Add new sponsor |  | 2024-05-02 | 2024-05-02
OSP1-8 | Build IRS Table Process
OSP1-9 | Add new eligible PI |  | 2024-05-02 |  | 2024-05-02 | 2024-05-02
OSP2 | VP/Board of Trustees Reports: | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OSP2-1 | USGM0006 |  | 2024-05-02 | 2024-05-02
OSP2-2 | USGM0007 |  | 2024-05-02 | 2024-05-02
OSP2-3 | USGM0008 |  | 2024-05-02 | 2024-05-02
OSP2-4 | USGM0009 |  | 2024-05-02 | 2024-05-02
OSP2-5 | USGM0010 |  | 2024-05-02 | 2024-05-02
OSP2-6 | USGM0011 |  | 2024-05-02 | 2024-05-02
OSP3 | Web Applications: | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OSP3-1 | eProposal |  | 2024-04-24 | 2024-04-24
OSP3-2 | eAward |  | 2024-05-02 | 2024-05-02
OSP3-3 | Research Portal |  | 2024-05-02 | 2024-05-02

## PC
Financial Services
|  | Items to Test: |  | 81 |  | Issue Found |  | 8 |  | User Test |  | 0
|  | Items Tested: |  | 77 |  | UIT - Not Started |  | 0 |  | Resolved by UIT |  | 4
|  | Performs as Expected |  | 69 |  | UIT - In Process |  | 8
PCARD |  | Total Items | Tested | Performs as Expected | Issue Found | UIT - Not Started | UIT - In Process | User Test | Resolved by UIT | Hold | Post Upgrade | JIRA # | Comments
Items to Test |  | 81 | 77 | 69 | 8 | 0 | 8 | 0 | 4 | 0 | 2 | 13
PC1 | PCARD PORTAL (PRO) - Employees | 6 | 6 | 5 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1
PC1-1 | Add new |  | 2024-04-24 | 2024-04-24
PC1-2 | Existing - Add training |  | 2024-04-24 | 2024-04-24
PC1-3 | Create card |  | 2024-04-19 |  | 2024-04-19 |  | 2024-04-19 |  |  |  |  | FIN-9033, FIN-9037, FIN 9045
PC1-4 | Duplicate Card |  | 2024-04-24 | 2024-04-24
PC1-5 | Issues - Add Inquiry |  | 2024-04-24 | 2024-04-24
PC1-6 | Add - Violation |  | 2024-04-24 | 2024-04-24
PC2 | PCARD PORTAL (PRO) - Cards | 9 | 9 | 8 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 2
PC2-1 | Update information |  | 2024-04-24 | 2024-04-24
PC2-2 | Change default chartfield |  | 2024-04-24 | 2024-04-24
PC2-3 | Change limits |  | 2024-04-24 | 2024-04-24
PC2-4 | Add/delete reallocator |  | 2024-04-24 | 2024-04-24
PC2-5 | Add/delete chartfields |  | 2024-04-24 | 2024-04-24
PC2-6 | Send chartfields to excel |  | 2024-04-19 | 2024-04-19 |  |  |  |  | Yes |  |  | FIN-9036 , FIN-9037
PC2-7 | Add exemptions |  | 2024-04-24 | 2024-04-24
PC2-8 | Add Permission |  | 2024-04-24 | 2024-04-24
PC2-9 | Change PCard's Default Chartfield & Org as an auditor |  | 2024-04-22 |  | 2024-04-22 |  | 2024-04-23 |  |  |  |  | FIN-9040
PC3 | PCARD PORTAL (PRO) - Department | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1
PC3-1 | Add new department |  | 2024-04-24 | 2024-04-24
PC3-2 | Existing Dept - Update information |  | 2024-04-19 | 2024-04-19 |  |  |  |  | Yes |  | Yes | FIN-9038
PC3-3 | Audit History - add audit |  | 2024-04-24 | 2024-04-24
PC3-4 | Add/view attachments |  | 2024-04-24 | 2024-04-24
PC3-5 | Dept Notes - Add note/upload attachment |  | 2024-04-24 | 2024-04-24
PC4 | PCARD PORTAL (PRO) - Audits | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PC4-1 | Quick Audit Entry - Gen Info-add note |  | 2024-04-24 | 2024-04-24
PC4-2 | Dept Audit Relationship - Add dept |  | 2024-04-24 | 2024-04-24
PC5 | PCARD PORTAL (PRO) - Maintenance | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
PC5-1 | Pcard Code Maintenance |  | 2024-04-24 | 2024-04-24
PC5-2 | -Inquiries |  | 2024-04-24 | 2024-04-24
PC5-3 | -Violations |  | 2024-04-24 | 2024-04-24
PC5-4 | -Cancellation |  | 2024-04-24 | 2024-04-24
PC5-5 | -Exemptions |  | 2024-04-24 | 2024-04-24
PC5-6 | Duplicate Card |  | 2024-04-24 | 2024-04-24
PC5-7 | Cancel Card |  | 2024-04-24 | 2024-04-24
PC5-8 | Un-Cancel Card |  | 2024-04-24 | 2024-04-24
PC5-9 | Universal Reallocator |  | 2024-04-23 | 2024-04-23 | [6 empty] | Yes | FIN-9049 | Found issue but not a PUM 50 issue
PC5-10 | Special Rights |  | 2024-04-24 | 2024-04-24
PC5-11 | Audit Reports - Run |  | 2024-04-24 | 2024-04-24
PC6 | PCARD PORTAL (PRO) - Chartfield Validation - | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PC6-1 | Invalid - to excel |  | 2024-04-24 | 2024-04-24
PC6-2 | Run validation |  | 2024-04-24 | 2024-04-24
PC6-3 | Invalid Chartfield Search - Indv CH |  | 2024-04-24 | 2024-04-24
PC6-4 | PCARD CF Validation |  | 2024-04-24 | 2024-04-24
PC7 | PCARD - Current Transactions Tab | 6 | 6 | 4 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 2
PC7-1 | Links to "Help" "Forms" work |  | 2024-04-30 | 2024-04-30
PC7-2 | Chartfield List to Excel |  | 2024-04-30 | 2024-04-30
PC7-3 | Transactions to Excel |  | 2024-04-30 | 2024-04-30
PC7-4 | Sort by Amt, Merchant, etc. |  | 2024-04-30 | 2024-04-30
PC7-5 | Select to Default |  | 2024-04-24 |  | 2024-04-24 |  | 2024-04-30 |  |  |  |  | FIN-9056
PC7-6 | Select to Alternate |  | 2024-04-24 |  | 2024-04-24 |  | 2024-04-30 |  |  |  |  | FIN-9057
PC8 | PCARD - Reallocations Tab | 11 | 11 | 9 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 2
PC8-1 | Account and A/U links work |  | 2024-04-30 | 2024-04-30
PC8-2 | Reallocate to multiple chartfields (running totals box correct) |  | 2024-04-24 |  | 2024-04-24 |  | 2024-04-30 |  |  |  |  | FIN-9058
PC8-3 | Department Reference |  | 2024-04-30 | 2024-04-30
PC8-4 | Error message works |  | 2024-04-30 | 2024-04-30
PC8-5 | Error hover button |  | 2024-04-30 | 2024-04-30
PC8-6 | Back to Transactions |  | 2024-04-30 | 2024-04-30
PC8-7 | Submit/Next |  | 2024-04-30 | 2024-04-30
PC8-8 | Next Transaction |  | 2024-04-30 |  | 2024-04-30 |  | 2024-04-30 |  |  |  |  | FIN-9052
PC8-9 | Delete a single line |  | 2024-04-30 | 2024-04-30
PC8-10 | Clear All to remove status |  | 2024-04-30 | 2024-04-30
PC8-11 | Validation is accurate (esp. on projects) |  | 2024-04-30 | 2024-04-30
PC9 | Monthly Statements | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PC9-1 | Run reports |  | 2024-04-30 | 2024-04-30
PC10 | Card Information | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PC10-1 | Verify information |  | 2024-04-30 | 2024-04-30
PC11 | Reporting Tools - Query Viewer - to Excel | 21 | 21 | 19 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 4
PC11-1 | Pcard AP Data Analysis |  | 2024-04-30 | 2024-04-30
PC11-2 | Pcard Audit Dates Rotation - PRO |  | 2024-04-30 | 2024-04-30
PC11-3 | Pcard CH Exemptions - PRO |  | 2024-04-30 | 2024-04-30
PC11-4 | Pcard CH List Real - PRO |  | 2024-04-30 |  | 2024-04-30 |  | 2024-04-30 |  |  |  |  | FIN-9053
PC11-5 | Pcard CH Profile - PRO |  | 2024-04-30 | 2024-04-30 |  |  |  |  | Yes |  |  | FIN-9054 | UIT cannot replicate
PC11-6 | Pcard Curr Reallocations |  | 2024-04-30 | 2024-04-30 |  |  |  |  | Yes |  |  | FIN-9055
PC11-7 | Pcard Default CF Active - PRO |  | 2024-04-30 | 2024-04-30
PC11-8 | Pcard Depts Missing SetIDS |  | 2024-04-30 | 2024-04-30
PC11-9 | Pcard Dept Audit Relation - PRO |  | 2024-04-30 | 2024-04-30
PC11-10 | Pcard Hlth Sci Vendor Org Rlup |  | 2024-04-30 | 2024-04-30
PC11-11 | Pcard Inactive Employee - PRO |  | 2024-04-30 | 2024-04-30
PC11-12 | Pcard Inactive Reallocators |  | 2024-04-30 | 2024-04-30
PC11-13 | Pcard Inqy Viol - PRO |  | 2024-04-30 | 2024-04-30
PC11-14 | Pcard JPMC Vendor List |  | 2024-04-30 |  | 2024-04-30 |  | 2024-04-30 |  |  |  |  | FIN-9053, FIN-9068
PC11-15 | Pcard Missing Default |  | 2024-04-30 | 2024-04-30
PC11-16 | Pcard Reallocators by CH - PRO |  | 2024-04-30 | 2024-04-30
PC11-17 | Pcard Real Chartfields - PRO |  | 2024-04-30 | 2024-04-30
PC11-18 | Pcard Scan Org Tbl - PRO |  | 2024-04-30 | 2024-04-30
PC11-19 | Pcard Stmt Recp Active Crd - PRO |  | 2024-04-30 | 2024-04-30
PC11-20 | Pcard Training - PRO |  | 2024-04-30 | 2024-04-30
PC11-21 | Pcard Trans1 by Date Range |  | 2024-04-30 | 2024-04-30
PC12 | U of U Applications - Maintain Pcard | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PC12-1 | Process Download Trans - FIS Test
PC12-2 | Print Past Summary Report
PC12-3 | Month-end Trans Purge
PC12-4 | Month-end Set Reviewed

## PT
Financial Services
|  | Items to Test: |  | 45 |  | Issue Found |  | 1 |  | User Test |  | 0
|  | Items Tested: |  | 40 |  | UIT - Not Started |  | 0 |  | Resolved by UIT |  | 1
|  | Performs as Expected |  | 39 |  | UIT - In Process |  | 1
Property Accounting |  | Total Items | Tested | Performs as Expected | Issue Found | UIT - Not Started | UIT - In Process | User Test | Resolved by UIT | Hold | Post Upgrade | JIRA # | Comments
Items to Test |  | 45 | 40 | 39 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1
PT1 | DEPRECIATION | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PT1-1 | DEPRECIATION CALCULATION AMDPCALC |  | 2024-04-30 | 2024-04-30
PT1-2 | ACCOUNTING ENTRY CREATION AMAEDIST |  | 2024-05-01 | 2024-05-01
PT1-3 | DEPRECIATION CLOSE AMDPCLOS |  | 2024-05-01 | 2024-05-01
PT1-4 | LOAD DEPR REPORTING TABLE LOAD DEPR RPT |  | 2024-05-01 | 2024-05-01
PT1-5 | LOAD NET BOOK VALUE TABLE AMLDNBVT |  | 2024-05-01 | 2024-05-01
PT2 | ASSETS | 6 | 6 | 5 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1
PT2-1 | ASSET LOCATION UPDATE USFA0021 |  | 2024-05-01 | 2024-05-01
PT2-2 | UPDATE ACQUISITION PROJECT USFA001 |  | 2024-05-01 | 2024-05-01
PT2-3 | MASS CHANGE |  | 2024-04-23 | 2024-04-23
PT2-4 | TRANSACTION LOADER AMIF1000 |  | 2024-04-23 | 2024-04-23
PT2-5 | WEEKLY RETRIEVAL FROM GL USFA0008 SQR |  | 2024-04-23 |  | 2024-04-23 |  | 2024-04-24 |  |  |  |  | FIN-9046
PT2-6 | AM/GL COMPARE USFA0007 SQR |  | 2024-04-23 | 2024-04-23
PT3 | REPORTS | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
PT3-1 | CAPITAL INVENTORY USFA0003 SQR |  | 2024-04-23 | 2024-04-23
PT3-2 | GOVERNMENT EQUIPMENT USFA0013 SQR |  | 2024-04-30 | 2024-04-30 |  |  |  |  | Yes
PT3-3 | UOFU ERROR REPORTS (ORG) USFA0016 SQR |  | 2024-04-23 | 2024-04-23
PT3-4 | UOFU ERROR REPORTS (COST) USFA0017 SQR |  | 2024-04-23 | 2024-04-23
PT3-5 | UOFU ERROR REPORTS (BOOK & COST) USFA0018 SQR |  | 2024-04-23 | 2024-04-23
PT4 | APPLICATIONS | 20 | 19 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PT4-1 | ADD ASSET |  | 2024-04-23 | 2024-04-23
PT4-2 | DELETE ASSET |  | 2024-04-23 | 2024-04-23
PT4-3 | ASSET CLASS/PROFILE ID DEPENDENCY (NEW ASSET) |  | 2024-05-01 | 2024-05-01
PT4-4 | ADD PARENT ASSET |  | 2024-05-01 | 2024-05-01
PT4-5 | DELETE PARENT ASSET |  | 2024-05-01 | 2024-05-01
PT4-6 | ADD CHILD ASSET |  | 2024-05-01 | 2024-05-01
PT4-7 | DELETE CHILD ASSET |  | 2024-05-01 | 2024-05-01
PT4-8 | RETIRE SALE |  | 2024-04-23 | 2024-04-23
PT4-9 | RETIRE SCRAP |  | 2024-04-23 | 2024-04-23
PT4-10 | RETIRE TRADE-IN |  | 2024-04-23 | 2024-04-23
PT4-11 | REINSTATE |  | 2024-04-23 | 2024-04-23
PT4-12 | ADJUST |  | 2024-04-23 | 2024-04-23
PT4-13 | TRANSFER INTRA |  | 2024-04-23 | 2024-04-23
PT4-14 | TRANSFER BU01 TO BU02 |  | 2024-04-30 | 2024-04-30
PT4-15 | ADD ASSET THRU UU ACQ PROJECT |  | 2024-04-30 | 2024-04-30
PT4-16 | CHANGE LOCATION |  | 2024-04-23 | 2024-04-23
PT4-17 | CHANGE LIFE |  | 2024-04-30 | 2024-04-30
PT4-18 | CHANGE PROFILE |  | 2024-04-30 | 2024-04-30
PT4-19 | ADD NEW ORG IN CUSTODIAN |  | 2024-04-23 | 2024-04-23
PT4-20 | ADD NEW MANUFACTURER
PT5 | NET BOOK VALUE | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PT5-1 | ADMP2100 NET BOOK VALUE |  | 2024-04-30 | 2024-04-30
PT6 | RFTrack Feeds | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PT6-1 | Import Location USFA0022
PT6-2 | Export Asset USFA0023
PT6-3 | Import Assets USFA0024
PT | Queries | 5 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PT7-1 | AM_BATCH_RETRIEVAL_REPORT |  | 2024-04-23 | 2024-04-23
PT7-2 | AM_CAPITAL_EQUIPMENT_LIST |  | 2024-04-23 | 2024-04-23
PT7-3 | UUAM0008_AP_SNEAK_PEEK |  | 2024-04-23 | 2024-04-23
PT7-3 | FY_UNPOSTED_VOUCHERS |  | 2024-04-23 | 2024-04-23
PT7-4 | Book Compare

## PR
Financial Services
|  | Items to Test: |  | 16 |  | Issue Found |  | 0 |  | User Test |  | 0
|  | Items Tested: |  | 16 |  | UIT - Not Started |  | 0 |  | Resolved by UIT |  | 0
|  | Performs as Expected |  | 16 |  | UIT - In Process |  | 0
Purchasing |  | Total Items | Tested | Performs as Expected | Issue Found | UIT - Not Started | UIT - In Process | User Test | Resolved by UIT | Hold | Post Upgrade | JIRA # | Comments
Items to Test |  | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR1 | Purchase Orders | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR1-1 | PO calculation |  | 2024-04-26 | 2024-04-26
PR1-2 | PO creation |  | 2024-04-26 | 2024-04-26
PR1-3 | PO budget check |  | 2024-04-26 | 2024-04-26
PR1-4 | PO document tolerance |  | 2024-04-26 | 2024-04-26
PR1-5 | PO print |  | 2024-04-26 | 2024-04-26
PR1-6 | PO dispatch |  | 2024-04-26 | 2024-04-26
PR1-7 | PO workbench |  | 2024-04-26 | 2024-04-26
PR2 | Vouchers | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR2-1 | Voucher re-budget check |  | 2024-05-01 | 2024-05-01
PR2-2 | Recurring voucher contract entry (PO contract stage) |  | 2024-05-01 | 2024-05-01
PR2-3 | Voucher lookup (web) |  | 2024-05-01 | 2024-05-01
PR3 | Maintain Vendors | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR3-1 | Vendor add |  | VM1 | VM1
PR3-2 | Vendor modification |  | VM1 | VM1
PR3-3 | Vendor lookup (web) |  | 2024-05-01 | 2024-05-01
PR4 | Other | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR4-1 | Ship-to code add and update |  | 2024-05-01 | 2024-05-01
PR4-2 | Where Art Thou (UU_WAT_RPT) |  | 2024-05-01 | 2024-05-01
PR5 | UShop Integration | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR5-1 | PURCHASE ORDER EXPORT |  | US2 | US2

## TX
Financial Services
|  | Items to Test: |  | 23 |  | Issue Found |  | 0 |  | User Test |  | 0
|  | Items Tested: |  | 10 |  | UIT - Not Started |  | 0 |  | Resolved by UIT |  | 0
|  | Performs as Expected |  | 10 |  | UIT - In Process |  | 0
Tax Services |  | Total Items | Tested | Performs as Expected | Issue Found | UIT - Not Started | UIT - In Process | User Test | Resolved by UIT | Hold | Post Upgrade | JIRA # | Comments
Items to Test |  | 23 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TX1 | Withholding Processes | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TX1-1 | Post Withholdings |  | 2024-04-19 | 2024-04-19
TX1-2 | Withholding Adjustment |  | 2024-04-19 | 2024-04-19
TX1-3 | Update Withholdings |  | 2024-04-19 | 2024-04-19
TX1-4 | Withholding 1099 Report Post |  | 2024-04-19 | 2024-04-19
TX1-5 | Withholding 1099 Report |  | 2024-04-19 | 2024-04-19
TX1-6 | 1099 to Send Detail |  | 2024-04-19 | 2024-04-19
TX1-7 | Print 1099 Copy B |  | 2024-04-19 | 2024-04-19
TX1-8 | Withholding Sent File |  | 2024-04-19 | 2024-04-19
TX1-9 | Withholding Control Report |  | 2024-04-19 | 2024-04-19
TX1-10 | Withholding 1099 Report (APX1099)(BI Publisher) |  | 2024-04-19 | 2024-04-19
TX2 | Sales Tax Application | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TX2-1 | Department Entry
TX2-2 | Tax Rate Report
TX2-3 | Department Report
TX2-4 | Upload Tax Tables
TX2-5 | Add Sales Tax Outlet
TX2-6 | Delete Sales Tax Outlet
TX2-7 | Look up Sales Tax Department
TX2-8 | Add Sales Tax Department
TX2-9 | Notifications
TX2-10 | Detail Department Submissions
TX2-11 | Generate Monthly Flat File
TX2-12 | Missing Report
TX2-13 | Create PDF Reports

## TR
Financial Services
|  | Items to Test: |  | 13 |  | Issue Found |  | 0 |  | User Test |  | 0
|  | Items Tested: |  | 12 |  | UIT - Not Started |  | 0 |  | Resolved by UIT |  | 0
|  | Performs as Expected |  | 12 |  | UIT - In Process |  | 0
Travel & Reimbursement Services |  | Total Items | Tested | Performs as Expected | Issue Found | UIT - Not Started | UIT - In Process | User Test | Resolved by UIT | Hold | Post Upgrade | JIRA # | Comments
Items to Test |  | 13 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TR1 | Travel Accounting | 7 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TR1-1 | Concur AP/GL Extract File (SAE)
TR1-2 | Concur CSA: add Concur user(s) |  | 2024-04-26 | 2024-04-26
TR1-3 | Concur CSA: add Concur user with delegate(s) APPROVER |  | 2024-04-26 | 2024-04-26
TR1-4 | Concur CSA: add Concur user with delegate(s) PLANNER |  | 2024-04-26 | 2024-04-26
TR1-5 | Concur CSA: add Concur user with Supervisor override |  | 2024-04-26 | 2024-04-26
TR1-6 | Concur CSA: add Concur user with ADSC override |  | 2024-04-26 | 2024-04-26
TR1-7 | Concur CSA: modify Concur user(s) |  | 2024-04-26 | 2024-04-26
TR2 | ePR - EM | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TR2-1 | Create New EM Request - New Vendor |  | 2024-04-26 | 2024-04-26
TR2-2 | Create New EM Request - Campus mail |  | 2024-04-26 | 2024-04-26
TR2-3 | Create New EM Request - Hold for Pickup |  | 2024-04-26 | 2024-04-26
TR2-4 | Create New EM Request - ACH |  | 2024-04-26 | 2024-04-26
TR2-5 | Test Address 500 process |  | 2024-04-26 | 2024-04-26
TR2-6 | EDI FEED |  | 2024-04-26 | 2024-04-26

## UNI
Financial & Business Services
|  | Items to Test: |  | 3 |  | Issue Found |  | 1 |  | User Test |  | 0
|  | Items Tested: |  | 2 |  | UIT - Not Started |  | 0 |  | Resolved by UIT |  | 0
|  | Performs as Expected |  | 1 |  | UIT - In Process |  | 1
Unifier |  | Total Items | Tested | Performs as Expected | Issue Found | UIT - Not Started | UIT - In Process | User Test | Resolved by UIT | Hold | Post Upgrade | JIRA # | Comments
Items to Test |  | 3 | 2 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1
UNI | Unifier | 3 | 2 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1
UNI-1 | Import invoices into Unifier
UNI-2 | Unifier PeopleSoft Vendor Integration |  | 2024-04-30 | 2024-04-30
UNI-3 | Unifier PeopleSoft Pament Integration |  | 2024-04-30 |  | 2024-04-30 |  | 2024-04-30 |  |  |  |  | FIN-9051

## UH
University of Utah Health
|  | Items to Test: |  | 54 |  | Issue Found |  | 0 |  | User Test |  | 0
|  | Items Tested: |  | 11 |  | UIT - Not Started |  | 0 |  | Resolved by UIT |  | 1
|  | Performs as Expected |  | 11 |  | UIT - In Process |  | 0
University Hospital Accounting |  | Total Items | Tested | Performs as Expected | Issue Found | UIT - Not Started | UIT - In Process | User Test | Resolved by UIT | Hold | Post Upgrade | JIRA # | Comments
|  | 54 | 11 | 11 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
UH1 | Journals | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UH1-1 | Reformat external journals
UH1-2 | External journal load
UH1-3 | Journal entry - Add
UH1-4 | Journal entry - Edit
UH1-5 | Journal entry - Delete
UH2 | Budget Journal | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UH2-1 | Budget Journal - Add
UH2-2 | Budget Journal - Copy
UH2-3 | Budget Journal - Edit
UH2-4 | Budget Journal - Delete
UH2-5 | Budget Journal - Post
UH3 | Actual Journal | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UH3-1 | Actual Journal - Add
UH3-2 | Actual Journal - Copy
UH3-3 | Actual Journal - Edit
UH3-4 | Actual Journal - Delete
UH3-5 | Actual Journal - Post
UH3-6 | Generate Actual Journal Reversal
UH4 | Stat Journal | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UH4-1 | Stat Journal - Add
UH4-2 | Stat Journal - Copy
UH4-3 | Stat Journal - Edit
UH4-4 | Stat Journal - Delete
UH4-5 | Stat Journal - Post
UH5 | Allocations | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UH5-1 | Allocations - Add
UH5-2 | Allocations - Copy
UH5-3 | Allocations - Edit
UH5-4 | Allocations - Delete
UH5-5 | Allocations - Execute
UH6 | Queries | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UH6-1 | Queries
UH7 | nVision Reports | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UH7-1 | nVision Reports - Add
UH7-2 | nVision Reports - Modify
UH7-3 | nVision Reports - Run
UH7-4 | nVision Reports - Define Scope
UH7-5 | nVision Reports Drilldown
UH8 | Org Id | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UH8-1 | Org Id - Add
UH8-2 | Org Id - Change
UH8-3 | Org Id - Inactivate
UH9 | Account | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UH9-1 | Account - Add
UH9-2 | Account - Change
UH9-3 | Account - Inactivate
UH10 | Trees | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UH10-1 | Trees - Add
UH10-2 | Trees - Copy
UH10-3 | Trees - Change
UH10-4 | Trees - Delete
UH10-5 | Trees - Audit
UH11 | Assets | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
UH11-1 | DEPRECIATION CALCULATION |  | 2024-04-19 | 2024-04-19
UH11-2 | ACCOUNTING ENTRY CREATION |  | 2024-04-19 | 2024-04-19
UH11-3 | LOAD DEPR REPORTING TABLE LOAD DEPR RPT |  | 2024-04-19 | 2024-04-19
UH11-4 | LOAD NET BOOK VALUE TABLE |  | 2024-04-19 | 2024-04-19
UH11-5 | DEPRECIATION CLOSE |  | 2024-04-19 | 2024-04-19
UH11-6 | PROCESS ALLOCATION |  | 2024-04-19 | 2024-04-19
UH11-7 | LOAD ASSETS REQUEST |  | 2024-04-18 | 2024-05-02 |  |  |  |  | Yes |  |  | FIN-9031
UH11-8 | RETRIEVE INFO FROM AP/PO |  | 2024-04-19 | 2024-04-19
UH11-9 | LOAD - UNITIZE ASSETS |  | 2024-04-19 | 2024-04-19
UH11-10 | LOAD TRANSACTIONS INTO AM |  | 2024-04-19 | 2024-04-19
UH11-11 | DEPRECIATION REPORT |  | 2024-04-19 | 2024-04-19

## US
Financial Services
|  | Items to Test: |  | 8 |  | Issue Found |  | 0 |  | User Test |  | 0
|  | Items Tested: |  | 8 |  | UIT - Not Started |  | 0 |  | Resolved by UIT |  | 0
|  | Performs as Expected |  | 8 |  | UIT - In Process |  | 0
UShop |  | Total Items | Tested | Performs as Expected | Issue Found | UIT - Not Started | UIT - In Process | User Test | Resolved by UIT | Hold | Post Upgrade | JIRA # | Comments
Items to Test |  | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US! | USHOP | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US1-1 | SUPPLIER IMPORT - accounts payable/purchasing should test in addition to ushop |  | 2024-04-30 | 2024-04-30
US1-2 | USER IMPORT |  | 2024-04-30 | 2024-04-30
US1-3 | CUSTOM FIELD INTEGRATION |  | 2024-04-30 | 2024-04-30
US1-4 | PR VALIDATION |  | 2024-04-30 | 2024-04-30
US1-5 | Create new User Role |  | 2024-04-30 | 2024-04-30
US1-6 | Vendor Type Tag Table (Ushop Applications>Use>Vendor Type Tag) |  | 2024-04-30 | 2024-04-30
US1-7 | PO export |  | 2024-04-30 | 2024-04-30
US1-8 | Invoice export |  | 2024-04-30 | 2024-04-30
US2 | USHOP - Phase 2 - After Jaggaer Upgrade | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US2-1 | SUPPLIER IMPORT - accounts payable/purchasing should test in addition to ushop
US2-2 | USER IMPORT
US2-3 | CUSTOM FIELD INTEGRATION
US2-4 | PR VALIDATION
US2-5 | Create new User Role
US2-6 | Vendor Type Tag Table (Ushop Applications>Use>Vendor Type Tag)
US2-7 | PO export
US2-8 | Invoice export

## VMT
Financial & Business Services
|  | Items to Test: |  | 30 |  | Issue Found |  | 0 |  | User Test |  | 0
|  | Items Tested: |  | 30 |  | UIT - Not Started |  | 0 |  | Resolved by UIT |  | 0
|  | Performs as Expected |  | 30 |  | UIT - In Process |  | 0
Vendor Maintenance |  | Total Items | Tested | Performs as Expected | Issue Found | UIT - Not Started | UIT - In Process | User Test | Resolved by UIT | Hold | Post Upgrade | JIRA # | Comments
Items to Test |  | 30 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
VM1 | MAINTAIN VENDORS | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
VM1-1 | FIND AN EXISTING VENDOR |  | 2024-04-23 | 2024-04-23
VM1-2 | ADD A NEW ADDRESS |  | 2024-04-23 | 2024-04-23
VM1-3 | ADD A NEW LOCATION |  | 2024-04-23 | 2024-04-23
VM1-4 | ADD A NEW 1099 CLASS |  | 2024-04-23 | 2024-04-23
VM1-5 | ADD AN ALTERNATE NAME |  | 2024-04-23 | 2024-04-23
VM1-6 | CHANGE REMIT TO VENDOR ON LOCATION |  | 2024-04-23 | 2024-04-23
VM1-7 | ADD A NEW VENDOR |  | 2024-04-23 | 2024-04-23
VM1-8 | DELETE A VENDOR |  | 2024-04-23 | 2024-04-23
VM1-9 | INACTIVATE AN EXISTING VENDOR |  | 2024-04-23 | 2024-04-23
VM1-10 | ADD ACH |  | 2024-04-23 | 2024-04-23
VM1-11 | ADD CONTACT |  | 2024-04-23 | 2024-04-23
VM1-12 | ADD A WITHHOLDING ALTERNATE NAME |  | 2024-04-23 | 2024-04-23
VM1-13 | SHORTNAME NUMBERING (FOR SHORTNAMES THAT WOULD BE THE SAME, EX: SMITHMICHA-001, 002, 003, ETC.) |  | 2024-04-23 | 2024-04-23
VM1-14 | UPDATE A SUPPLIER’S NAME |  | 2024-04-23 | 2024-04-23
VM1-15 | PAYMENT TERMS |  | 2024-04-23 | 2024-04-23
VM1-16 | SUPPLIER TYPE (IND, COR, PAR, ETC.) |  | 2024-04-23 | 2024-04-23
VM1-17 | PAYMENT HANDLING CODE |  | 2024-04-23 | 2024-04-23
VM1-18 | CONTACT TAB (FOR ACH, SUA PAYMENT METHODS) |  | 2024-04-23 | 2024-04-23
VM2 | WHAT HAS BEEN CUSTOMIZED | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
VM2-1 | THE "DELETE" CHECK BOX |  | 2024-04-23 | 2024-04-23
VM2-2 | VENDOR TIN |  | 2024-04-23 | 2024-04-23
VM2-3 | EMPLID |  | 2024-04-23 | 2024-04-23
VM2-4 | ENTERED, BY/MAINTAINED, BY/ LAST UPDATE |  | 2024-04-23 | 2024-04-23
VM2-5 | FORM W-9 CHECK BOX/DATE W-9 RECEIVED |  | 2024-04-23 | 2024-04-23
VM2-6 | APPROVAL DATE/BY |  | 2024-04-23 | 2024-04-23
VM2-7 | ACH PAYMENT METHOD UPDATES, |  | 2024-04-23 | 2024-04-23
VM3 | Set up Scholarship/Fellowships contracts, then notify Accounts Payable | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
VM3-1 | CREATE A NON PO CONTRACT - AP BU 01 |  | 2024-05-01 | 2024-05-01
VM3-2 | CREATE A CONTRACT WITH NEGATIVE LINES (WITHHOLDING) - AP BU 01 |  | 2024-05-01 | 2024-05-01
VM3-3 | CREATE RECURRING RELEASES FOR PO CONTRACTS - AP BU 27 |  | 2024-05-01 | 2024-05-01
VM3-4 | CREATE RECURRING RELEASES FOR CONTRACTS WITH NEGATIVE LINES (WITHHOLDING) - AP BU 27 |  | 2024-05-01 | 2024-05-01
VM4 | UofU APP | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
VM4-1 | USAP0012 (VENDOR DELTE/SQR) |  | 2024-05-01 | 2024-05-01 | [6 empty] | Yes

## Total
Financial Services
| Items to Test: |  | 581 |  | Issue Found |  | 16 |  | User Test |  | 0
| Items Tested: |  | 462 |  | UIT - Not Started |  | 2 |  | Resolved by UIT |  | 8
| Performs as Expected |  | 446 |  | UIT - In Process |  | 14
UPGRADE TOTALS | Total Items | Tested | Performs as Expected | Issue Found | UIT - Not Started | UIT - In Process | User Test | Resolved by UIT | Hold | Post Upgrade | Percent Complete | Comments
| 581 | 462 | 446 | 16 | 2 | 14 | 0 | 8 | 0 | 5 | 77.62%
Accounts Payable | 112 | 103 | 103 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 91.96%
Financial Services Technical Support | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 100%
Financial Reporting and Accounting | 45 | 45 | 44 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 97.78%
Grants and Contracts Accounting | 100 | 73 | 69 | 4 | 1 | 3 | 0 | 0 | 0 | 0 | 69%
Bursars Office | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Office of Sponsored Projects | 18 | 17 | 16 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 88.89%
PCard | 81 | 77 | 69 | 8 | 0 | 8 | 0 | 4 | 0 | 2 | 85.19%
Property Accouting | 45 | 40 | 39 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 86.67%
Purchasing | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100%
Tax Services | 23 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43.48%
Travel Services | 13 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92.31%
Unifier | 3 | 2 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 33.33%
University Hospital Accounting | 54 | 11 | 11 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 20.37%
UShop | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100%
Vendor Maintenance | 30 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 100%